## Index
AWP Requirement Index
DR00-01 Requirement List
Data Requirement Number | Requirement Name | Data Table | Table Name | Directory Name
DR010 | AWP Master Index | 01 | Project Information | DR010-01 Project Information |  | AWP Data Requirements Index
DR010 | AWP Master Index | 02 | CWAs | DR010-02 CWAs | DR010 | AWP Master Index | DR120 | Document Control | DR230 | Contractor Scope Items
DR010 | AWP Master Index | 03 | CWPs | DR010-03 CWPs | DR020 | Project Schedule | DR140 | Estimating and Cost | DR260 | Constraints
DR010 | AWP Master Index | 04 | EWPs | DR010-04 EWPs | DR050 | Equipment Design | DR150 | Procurement | DR270 | Site Materials
DR010 | AWP Master Index | 05 | IWPs | DR010-05 IWPs | DR070 | Piping Design | DR170 | Structural Detailing | DR290 | Site Progress
DR010 | AWP Master Index | 06 | SWPs | DR010-06 SWPs | DR080 | 3D Modeling | DR180 | Steel Fabrication | DR310 | Completions
DR020 | Project Schedule | 01 | Schedule Activities | DR020-01 Schedule Activities | DR090 | Civil-Structural Design | DR190 | Pipe Detailing
DR050 | Equipment Design | 01 | Equipment List | DR050-01 Equipment List | DR100 | Electrical & Instrumentation Design | DR200 | Pipe Fabrication
DR070 | Piping Design | 01 | Line List | DR070-01 Line List
DR070 | Piping Design | 02 | Isometric List | DR070-02 Isometric List
DR070 | Piping Design | 03 | Tie-in List | DR070-03 Tie-in List | AWP Joint Working Group
DR070 | Piping Design | 04 | Pipe Support List | DR070-04 Pipe Support List | Phase I. Data Requirements Definition Team (2nd Half of 2019):
DR080 | 3D Modeling | 01 | Piping Components | DR080-01 Piping Components | · Tom Morris - ExxonMobil
DR080 | 3D Modeling | 02 | Generic Components | DR080-02 Generic Components | · Stephen Jones - Shell
DR090 | Civil-Structural Design | 01 | Structures List | DR090-01 Structures List | · Jacob Bubalo - Eastman
DR090 | Civil-Structural Design | 02 | Rebar | DR090-02 Rebar | · Manoj Dharwadkar - Dow
DR090 | Civil-Structural Design | 03 | Anchor Bolts | DR090-03 Anchor Bolts | · Tedd Weitzman - Construct-X
DR090 | Civil-Structural Design | 04 | Foundations | DR090-04 Foundations | · John Banda - Autodesk
DR100 | Electrical & Instrumentation Design | 01 | Cable Schedule | DR100-01 Cable Schedule | · Adam Messersmith - Kiewit
DR100 | Electrical & Instrumentation Design | 02 | Electrical Equipment | DR100-02 Electrical Equipment | · Srinivas Avantsa - AVEVA
DR100 | Electrical & Instrumentation Design | 03 | Instrument Index | DR100-03 Instrument Index | · Colin McIntyre - Bechtel
DR100 | Electrical & Instrumentation Design | 04 | Conduit | DR100-04 Conduit | · Ted Blackmon - Construct-X
DR100 | Electrical & Instrumentation Design | 05 | Cable Tray | DR100-05 Cable Tray | · Eric Crivella - Digital Construction Works
DR100 | Electrical & Instrumentation Design | 06 | Lighting & Devices | DR100-06 Lighting & Devices
DR100 | Electrical & Instrumentation Design | 07 | Electrical Heat Tracing | DR100-07 Electrical Heat Tracing | Phase II. Publication Team (1st Half of 2020):
DR120 | Document Control | 01 | Document Register | DR120-01 Document Register | · Tom Morris - ExxonMobil
DR120 | Document Control | 02 | Document to Entity | DR120-02 Document to Entity | · Stephen Jones - Shell
DR140 | Estimating and Cost | 01 | EWP Estimate | DR140-01 EWP Estimate | · Jacob Bubalo - Eastman
DR140 | Estimating and Cost | 02 | CWP Estimate | DR140-02 CWP Estimate | · Manoj Dharwadkar - Dow
DR150 | Procurement | 01 | Material Requisition Tracking | DR150-01 Material Requisition Tracking | · Tedd Weitzman - Construct-X
DR150 | Procurement | 02 | Purchase Order Line Items | DR150-02 Purchase Order Line Items | · John Banda - Autodesk
DR150 | Procurement | 03 | Supplier Purchase Order Shipments | DR150-03 Supplier Purchase Order Shipments | · Adam Messersmith - Kiewit
DR150 | Procurement | 04 | Supplier Load Detail | DR150-04 Supplier Load Detail | · Srinivas Avantsa - AVEVA
DR150 | Procurement | 05 | Supplier Container Detail | DR150-05 Supplier Container Detail | · Colin McIntyre - Bechtel
DR170 | Structural Detailing | 01 | Steel Detailing Deliverables | DR170-01 Steel Detailing Deliverables | · John Walker - Atlas RFID Solutions
DR170 | Structural Detailing | 02 | Steel Detail Drawings | DR170-02 Steel Detail Drawings | · Yong Cho - Georgia Institute of Technology
DR170 | Structural Detailing | 03 | Steel Piecemarks | DR170-03 Steel Piecemarks | · Eric Marks - Georgia Institute of Technology
DR170 | Structural Detailing | 04 | Steel 3D Model Relationship | DR170-04 Steel 3D Model Relationship
DR170 | Structural Detailing | 05 | Steel Connection Details | DR170-05 Steel Connection Details | Phase III. TO BE COMPLETED | Phase III. Industry’s Feedback from ExxonMobil Corporation, Shell Global Solutions US Inc., Fluor Corporation, Hexagon, O3 Solutions, Insight-AWP Inc. (Second Half 2021):
DR180 | Steel Fabrication | 01 | Steel Fabrication CWP Tracking | DR180-01 Steel Fabrication CWP Tracking
DR180 | Steel Fabrication | 02 | Steel Fabrication Details Tracking | DR180-02 Steel Fabrication Details Tracking
DR190 | Pipe Detailing | 01 | Pipe Isometric Detailing | DR190-01 Pipe Isometric Detailing |  | Joint Working Group
DR190 | Pipe Detailing | 02 | Pipe Isometric Transmittals | DR190-02 Pipe Isometric Transmittals |  | · Tom Morris, ExxonMobil Corporation
DR190 | Pipe Detailing | 03 | Pipe Spools | DR190-03 Pipe Spools |  | · Steve Jones, Shell Global Solutions US Inc.
DR200 | Pipe Fabrication | 01 | Pipe CWP Fabrication Delivery Requirements | DR200-01 Pipe CWP Fabrication Delivery Requirements |  | · Dario Rigaud, Fluor Corporation
DR200 | Pipe Fabrication | 02 | Pipe Spool Fabrication Tracking | DR200-02 Pipe Spool Fabrication Tracking |  | · Ajitesh Pahari, Fluor Corporation
DR230 | Contractor Scope Items | 01 | Contractor Scope | DR230-01 Contractor Scope |  | · Anabella Martin, Hilti Corporation
DR260 | Constraints | 01 | Constraints | DR260-01 Constraints |  | · Bob Wible, Construction Industry Institute
DR270 | Site Materials | 01 | Materials Location | DR270-01 Materials Location |  | · Chuck Mies, Autodesk, Inc.
DR270 | Site Materials | 02 | Material Receiving Report | DR270-02 Material Receiving Report |  | · Eric Crivella, The Dow Chemical Company
DR270 | Site Materials | 03 | Materials Inventory | DR270-03 Materials Inventory |  | · Eric Dechoz, Shell Global Solutions US Inc.
DR270 | Site Materials | 04 | Materials Issue | DR270-04 Materials Issue |  | · Gregorio Labbozzetta, Insight-AWP Inc.
DR290 | Site Progress | 01 | Rules of Credit | DR290-01 Rules of Credit |  | · Jay Moser, Shell Global Solutions US Inc.
DR290 | Site Progress | 02 | IWP Work Steps | DR290-02 IWP Work Steps |  | · John Banda, Autodesk, Inc.
DR290 | Site Progress | 03 | IWP Execution | DR290-03 IWP Execution |  | · John Fish, FB&D
DR290 | Site Progress | 04 | IWP Delays | DR290-04 IWP Delays |  | · Lloyd Rankin, Group ASI
DR310 | Completions | 01 | Sub-Systems Index | DR310-01 Sub-Systems Index |  | · Mark Mehta, iConstruct
DR310 | Completions | 02 | Test Packages | DR310-02 Test Packages |  | · Mick Hayashi, JGC Corporation
DR310 | Completions | 03 | Punch List Items | DR310-03 Punch List Items |  | · Nagendra Koripalli, XOM
DR310 | Completions | 04 | Check & Test Sheets | DR310-04 Check & Test Sheets |  | · Silvana Lara, Fluor Corporation
· Tedd Weitzman, Worley

## DR010-01
AWP Master Index
DR010-01 Project Information
Key | Tier | Field Name | Definition | Directory
PK | Required | Project ID | Unique project identifier | DR000-01 Requirements List
| Required | Project Name | Name of the project | DR010-01 Project Information
| Optional | Project Description | Description of the project | DR020-01 Schedule Activities
| Optional | Project Location | Location of project installation | DR050-01 Equipment List
DR070-01 Line List
DR080-01 Pipe Components
DR090-01 Structures List
DR100-01 Cable Schedule
DR120-01 Document Register
DR140-01 EWP Estimate
DR150-01 Material Requisition Tracking
DR170-01 Steel Detailing Deliverables
DR180-01 Steel Fabrication CWP Tracking
DR190-01 Pipe Isometric Detailing
DR200-01 Pipe CWP Fabrication Delivery Requirements
DR230-01 Contractor Scope
DR260-01 Constraints
DR270-01 Materials Location
DR290-01 Rules of Credit
DR310-01 Sub-Systems Index

## DR010-02
AWP Master Index
DR010-02 CWAs
Key | Tier | Field Name | Definition | Directory
PK | Required | Project ID | Unique project identifier | DR000-01 Requirements List
PK | Required | CWA | Unique Construction Work Area Identifier | DR010-01 Project Information
| Required | CWA Description | CWA description | DR020-01 Schedule Activities
| Optional | CWA GIS Boundary | GIS information defining the CWA | DR050-01 Equipment List
| Optional | CWA Ground Level | CWA above ground, below ground, or mixed | DR070-01 Line List
| Optional | CWA Plot Plan Drawing | Drawing number capturing the CWA plot delineation | DR080-01 Pipe Components
DR090-01 Structures List
DR100-01 Cable Schedule
DR120-01 Document Register
DR140-01 EWP Estimate
DR150-01 Material Requisition Tracking
DR170-01 Steel Detailing Deliverables
DR180-01 Steel Fabrication CWP Tracking
DR190-01 Pipe Isometric Detailing
DR200-01 Pipe CWP Fabrication Delivery Requirements
DR230-01 Contractor Scope
DR260-01 Constraints
DR270-01 Materials Location
DR290-01 Rules of Credit
DR310-01 Sub-Systems Index

## DR010-03
AWP Master Index
DR010-03 CWPs
Key | Tier | Field Name | Definition | Directory
PK | Required | Project ID | Unique project identifier | DR000-01 Requirements List
PK | Required | CWP | Unique construction work package identifier | DR010-01 Project Information
| Required | CWP Contract | Unique identifier of contract responsible for CWP execution | DR020-01 Schedule Activities
| Required | CWA | Unique construction work area identifier | DR050-01 Equipment List
| Required | CWP Description | CWP description | DR070-01 Line List
| Required | CWP Status | Status of the construction work package | DR080-01 Pipe Components
| Required | CWP Discipline | Discipline responsible for the execution of the CWP | DR090-01 Structures List
| Optional | CWP Type | Construction work package type (e.g., install, insulate, fabricate, etc.) | DR100-01 Cable Schedule
| Optional | CWP Estimate Hours | Current control budget construction workhours of the CWP (aligned to schedule) | DR120-01 Document Register
| Optional | CWP Revision | Current revision of the CWP | DR140-01 EWP Estimate
| Optional | CWP Sequence | Sequence of the CWP within the CWA (i.e., represents the Path of Construction) | DR150-01 Material Requisition Tracking
DR170-01 Steel Detailing Deliverables
DR180-01 Steel Fabrication CWP Tracking
DR190-01 Pipe Isometric Detailing
DR200-01 Pipe CWP Fabrication Delivery Requirements
DR230-01 Contractor Scope
DR260-01 Constraints
DR270-01 Materials Location
DR290-01 Rules of Credit
DR310-01 Sub-Systems Index

## DR010-04
AWP Master Index
DR010-04 EWPs
Key | Tier | Field Name | Definition | Directory
PK | Required | Project ID | Unique project identifier | DR000-01 Requirements List
PK | Required | EWP | Unique engineering work package identifier | DR010-01 Project Information
| Required | CWP | Unique construction work package identifier | DR020-01 Schedule Activities
| Required | EWP Description | Engineering work package description | DR050-01 Equipment List
| Required | EWP Discipline | Discipline responsible for EWP execution | DR070-01 Line List
| Required | EWP Status | Status of the engineering work package | DR080-01 Pipe Components
| Required | EWP Contract | Unique identifier of contract responsible for EWP execution | DR090-01 Structures List
| Optional | EWP Owner | Name responsible for EWP (typically the discipline lead) | DR100-01 Cable Schedule
| Optional | EWP Revision | Current revision of the EWP | DR120-01 Document Register
DR140-01 EWP Estimate
DR150-01 Material Requisition Tracking
DR170-01 Steel Detailing Deliverables
DR180-01 Steel Fabrication CWP Tracking
DR190-01 Pipe Isometric Detailing
DR200-01 Pipe CWP Fabrication Delivery Requirements
DR230-01 Contractor Scope
DR260-01 Constraints
DR270-01 Materials Location
DR290-01 Rules of Credit
DR310-01 Sub-Systems Index

## DR010-05
AWP Master Index
DR010-05 IWPs
Key | Tier | Field Name | Definition | Directory
PK | Required | Project ID | Unique project identifier | DR000-01 Requirements List
PK | Required | IWP | Unique installation work package identifier | DR010-01 Project Information
| Required | IWP Description | IWP description | DR020-01 Schedule Activities
| Required | IWP Discipline | IWP discipline | DR050-01 Equipment List
| Required | IWP Contract | Unique identifier of contract responsible for IWP execution | DR070-01 Line List
| Required | CWP | Unique construction work package identifier | DR080-01 Pipe Components
| Required | IWP Planner | WorkFace Planner responsible for the IWP | DR090-01 Structures List
| Optional | IWP Foreman | Foreman responsible for executing the IWP | DR100-01 Cable Schedule
| Optional | IWP General Foreman | General foreman responsible for overseeing execution of the IWP | DR120-01 Document Register
| Optional | IWP Superintendent | Superintendent responsible for overseeing execution of the IWP | DR140-01 EWP Estimate
| Required | IWP Status | Status of the IWP (e.g., in development, in execution, completed, etc.) | DR150-01 Material Requisition Tracking
| Required | IWP Forecast Start | Forecast schedule start date of the IWP | DR170-01 Steel Detailing Deliverables
| Required | IWP Forecast Completion | Forecast schedule completion date of the IWP | DR180-01 Steel Fabrication CWP Tracking
| Required | IWP Actual Start | Actual schedule start date of the IWP | DR190-01 Pipe Isometric Detailing
| Required | IWP Actual Completion | Actual schedule completion date of the IWP | DR200-01 Pipe CWP Fabrication Delivery Requirements
| Optional | IWP Estimate Hours | Current control budget construction workhours of the IWP | DR230-01 Contractor Scope
| Optional | IWP Revision | Current revision of the IWP | DR260-01 Constraints
| Optional | IWP Sequence | Sequence of the IWP within the CWP (i.e., represents the path of construction) | DR270-01 Materials Location
| Optional | IWP Type | Installation work package type (e.g., install, insulate, fabricate, etc.) | DR290-01 Rules of Credit
| Optional | IWP Key Quantity | Sum up of main quantity to install as part of the IWP | DR310-01 Sub-Systems Index
| Optional | IWP Key Quantity UOM | Unit of measurement for IWP key quantity (e.g., linear feet of pipe, tons of steel, etc.)

## DR010-06
AWP Master Index
DR010-06 SWPs
Key | Tier | Field Name | Definition | Directory
PK | Required | Project ID | Unique project identifier | DR000-01 Requirements List
PK | Required | SWP | Unique system work package identifier | DR010-01 Project Information
| Required | SWP Description | SWP description | DR020-01 Schedule Activities
| Required | SWP Discipline | SWP discipline | DR050-01 Equipment List
| Required | SWP Contract | Unique identifier of contract responsible for SWP execution | DR070-01 Line List
| Optional | Commissioning Zone ID | Unique commissioning zone identifier | DR080-01 Pipe Components
| Required | System ID | Unique turnover system identifier | DR090-01 Structures List
| Required | Sub-System ID | Unique turnover sub-system identifier | DR100-01 Cable Schedule
| Required | SWP Construction Manager | Construction Manager responsible for the SWP | DR120-01 Document Register
| Required | SWP Commissioning Manager | Commissioning Manager responsible for executing the SWP | DR140-01 EWP Estimate
| Required | SWP Status | Status of the SWP (e.g., in development, in execution, completed, etc.) | DR150-01 Material Requisition Tracking
| Required | SWP Forecast Start | Forecast schedule start date of the SWP | DR170-01 Steel Detailing Deliverables
| Required | SWP Forecast Completion | Forecast schedule completion date of the SWP | DR180-01 Steel Fabrication CWP Tracking
| Required | SWP Actual Start | Actual schedule start date of the SWP | DR190-01 Pipe Isometric Detailing
| Required | SWP Actual Completion | Actual schedule completion date of the SWP | DR200-01 Pipe CWP Fabrication Delivery Requirements
| Optional | Related CWP | Related construction work package | DR230-01 Contractor Scope
| Required | Related IWP | Related installation work package | DR260-01 Constraints
| Optional | Related Tag | Related Tag for the SWP | DR270-01 Materials Location
| Optional | SWP Estimate Hours | Current control budget construction workhours of the SWP | DR290-01 Rules of Credit
| Optional | SWP Revision | Current revision of the SWP | DR310-01 Sub-Systems Index
| Optional | SWP Sequence | Sequence of the SWP within the sub-system

## DR020-01
AWP Project Schedule
DR020-01 Schedule Activities
Key | Tier | Field Name | Definition | Directory
PK | Required | Project ID | Unique project identifier | DR000-01 Requirements List
PK | Required | Activity ID | Unique ID for the schedule activity | DR010-01 Project Information
| Required | Activity Name | Descriptive name for the schedule activity | DR020-01 Schedule Activities
| Required | WBS | Work breakdown structure code for the activity | DR050-01 Equipment List
| Required | Baseline Start Date | Baseline schedule start date of the activity | DR070-01 Line List
| Required | Baseline Completion Date | Baseline schedule completion date of the activity | DR080-01 Pipe Components
| Optional | Current Re-baselined Start | Current re-baselined schedule start date of the activity | DR090-01 Structures List
| Optional | Current Re-baselined Completion | Current re-baselined schedule completion date of the activity | DR100-01 Cable Schedule
| Required | Forecast Start | Forecast schedule start date of the activity | DR120-01 Document Register
| Required | Forecast Completion | Forecast schedule completion date of the activity | DR140-01 EWP Estimate
| Required | Actual Start | Actual schedule start date of the activity | DR150-01 Material Requisition Tracking
| Required | Actual Completion | Actual schedule completion date of the activity | DR170-01 Steel Detailing Deliverables
| Required | Early Start | Early schedule start date of the activity | DR180-01 Steel Fabrication CWP Tracking
| Required | Early Completion | Early schedule completion date of the activity | DR190-01 Pipe Isometric Detailing
| Required | Late Start | Late schedule start date of the activity | DR200-01 Pipe CWP Fabrication Delivery Requirements
| Required | Late Completion | Late schedule completion date of the activity | DR230-01 Contractor Scope
| Required | Total Float | Total float of the activity in days | DR260-01 Constraints
| Required | CWA | Unique construction work area identifier | DR270-01 Materials Location
| Required | CWP | Unique construction work package identifier | DR290-01 Rules of Credit
| Required | EWP | Unique engineering work package identifier | DR310-01 Sub-Systems Index
| Optional | IWP | Unique installation work package identifier
| Required | Estimate Hours | Current control budget construction workhours of the activity (CWA, CWP, EWP, IWP)
| Optional | Contract Reference | Contract information (e.g., contract identifier, contract release, etc.)
| Optional | Parent Activity ID | Unique identifier for the schedule parent activity
| Optional | Percent Complete | Percentage complete for the work activity

## DR050-01
AWP Equipment Design
DR050-01 Equipment List
Key | Tier | Field Name | Definition | Directory
PK | Required | Project ID | Unique project identifier | DR000-01 Requirements List
PK | Required | Tag | Unique tag number assigned to identify a project item | DR010-01 Project Information
| Required | Construction Requirement | Specifies if it is new or existing and to be refurbished or modified | DR020-01 Schedule Activities
| Required | CWA | Unique construction work area identifier | DR050-01 Equipment List
| Required | CWP | Unique construction work package identifier | DR070-01 Line List
| Required | EWP | Unique engineering work package identifier | DR080-01 Pipe Components
| Required | Equipment Type | Type of equipment | DR090-01 Structures List
| Optional | Fireproof Code | Code that specifies the type of fireproofing required | DR100-01 Cable Schedule
| Optional | Insulation Class - Channel | Type of insulation on tube side of tube exchanger | DR120-01 Document Register
| Optional | Insulation Class - Shell | Type of insulation on shell side of tube heat exchanger | DR140-01 EWP Estimate
| Required | Manufacturer | Manufacturer of tagged item | DR150-01 Material Requisition Tracking
| Optional | Motor | Tag of the motor on equipment. (e.g., pump compressor) | DR170-01 Steel Detailing Deliverables
| Optional | Paint Code | Code that provides the paint color and mill thickness requirements | DR180-01 Steel Fabrication CWP Tracking
| Required | PID | Piping and instrumentation diagram drawing number | DR190-01 Pipe Isometric Detailing
| Required | PO | Purchase order number | DR200-01 Pipe CWP Fabrication Delivery Requirements
| Optional | Requisition | Requisition number | DR230-01 Contractor Scope
| Optional | Equipment Revision | Current revision | DR260-01 Constraints
| Required | Skid | Skid tag number the equipment is part of | DR270-01 Materials Location
| Required | Sub-System ID | Unique turnover sub-system identifier | DR290-01 Rules of Credit
| Optional | Test Package ID | Unique test package identifier (e.g., hydrotest package) | DR310-01 Sub-Systems Index
| Optional | Tracing Code | Code that specifies the type of heat tracing required
| Required | Module | Module the component belongs to, when applicable
| Optional | Equipment Location Plan | Number of location drawing, i.e., (B01-xxxx-yyyyy)
| Optional | Responsible Discipline | Discipline responsible for the equipment
| Optional | Specification | Equipment specification number
| Optional | Weight | Weight of the item
| Optional | Weight UOM | Unit of measurement for weight of the item (e.g, TN, Lbs, MT, Kg, etc.)

## DR070-01
AWP Piping Design
DR070-01 Line List
Key | Tier | Field Name | Definition | Directory
PK | Required | Project ID | Unique project identifier | DR000-01 Requirements List
PK | Required | Line Number | Unique pipeline identifier per segment | DR010-01 Project Information
| Required | AG-UG | Is the pipeline above ground (AG) or underground (UG)? | DR020-01 Schedule Activities
| Required | Construction Requirement | Specifies whether it is new or existing and to be refurbished or modified | DR050-01 Equipment List
| Optional | From Tag | Tag number that this specific Tag is connected from | DR070-01 Line List
| Optional | Insulation Spec | Insulation specification of the item | DR080-01 Pipe Components
| Optional | Insulation Thickness | Insulation thickness of the item | DR090-01 Structures List
| Optional | Insulation Thickness UOM | Unit of measurement for insulation thickness (e.g., In, MM, etc.) | DR100-01 Cable Schedule
| Required | Nominal Size | Nominal size of the pipe | DR120-01 Document Register
| Required | Size UOM | Unit of measurement for size of the pipe (e.g., EA, LF, M, In, etc.) | DR140-01 EWP Estimate
| Optional | Paint Code | Code that provides the paint color and mill thickness requirements | DR150-01 Material Requisition Tracking
| Optional | PID Drawing Number(s) | Related piping and instrumentation diagram drawing number | DR170-01 Steel Detailing Deliverables
| Optional | PWHT | Is the pipeline post-weld heat treated? (Y or N) | DR180-01 Steel Fabrication CWP Tracking
| Optional | Service | Fluid code associated to the item | DR190-01 Pipe Isometric Detailing
| Required | Spec | Piping specification | DR200-01 Pipe CWP Fabrication Delivery Requirements
| Optional | To Tag | Tag number that this specific Tag is connected to | DR230-01 Contractor Scope
| Optional | Tracing Code | Code that specifies the type of heat tracing required | DR260-01 Constraints
| Required | Sub-System ID | Unique turnover sub-system identifier | DR270-01 Materials Location
| Optional | Test Pressure | Testing pressure | DR290-01 Rules of Credit
| Optional | Test Pressure UOM | Unit of measurement for testing pressure (e.g., PSI, Bar, Pa ) | DR310-01 Sub-Systems Index
| Optional | Test Temperature | Testing temperature
| Optional | Test Temperature UOM | Unit of measurement for testing temperature (e.g., F°, C°)
| Optional | Design Pressure | Design pressure
| Optional | Design Pressure UOM | Unit of measurement for design pressure (e.g., PSI, Bar, Pa )
| Optional | Design Temperature | Design temperature
| Optional | Design Temperature UOM | Unit of measurement for design temperature (e.g., F°, C°)
| Optional | Operating Pressure | Operating pressure
| Optional | Operating Pressure UOM | Unit of measurement for operating pressure (e.g., PSI, Bar, Pa )
| Optional | Operating Temperature | Operating temperature
| Optional | Operating Temperature UOM | Unit of measurement for operating temperature (e.g., F°, C°)
| Optional | Line Status | Status of the line (e.g., released to construction, etc.)
| Optional | Line Revision | Current revision

## DR070-02
AWP Piping Design
DR070-02 Isometric List
Key | Tier | Field Name | Definition | Directory
PK | Required | Project ID | Unique project identifier | DR000-01 Requirements List
PK | Required | Isometric Drawing | Piping isometric drawing number | DR010-01 Project Information
| Required | Line Number(s) | Pipeline ID | DR020-01 Schedule Activities
| Required | CWA | Unique construction work area identifier | DR050-01 Equipment List
| Required | CWP | Unique construction work package identifier | DR070-01 Line List
| Required | EWP | Unique engineering work package identifier | DR080-01 Pipe Components
| Required | Isometric Drawing Status | Status of issued isometric (e.g., issued for construction [IFC], IFI, IFR, etc.) | DR090-01 Structures List
| Required | Isometric Drawing Revision | Current revision of isometric drawing | DR100-01 Cable Schedule
DR120-01 Document Register
DR140-01 EWP Estimate
DR150-01 Material Requisition Tracking
DR170-01 Steel Detailing Deliverables
DR180-01 Steel Fabrication CWP Tracking
DR190-01 Pipe Isometric Detailing
DR200-01 Pipe CWP Fabrication Delivery Requirements
DR230-01 Contractor Scope
DR260-01 Constraints
DR270-01 Materials Location
DR290-01 Rules of Credit
DR310-01 Sub-Systems Index

## DR070-03
AWP Piping Design
DR070-03 Tie-in List
Key | Tier | Field Name | Definition | Directory
PK | Required | Project ID | Unique project identifier | DR000-01 Requirements List
PK | Required | Tie-in ID | Unique tie-in identifier from engineering | DR010-01 Project Information
| Required | CWA | Unique construction work area identifier | DR020-01 Schedule Activities
| Required | CWP | Unique construction work package identifier | DR050-01 Equipment List
| Required | EWP | Unique engineering work package identifier | DR070-01 Line List
| Required | Downtime | Downtime required? (Y or N) | DR080-01 Pipe Components
| Required | Construction Requirement | Specifies if whether is new or existing and to be refurbished or modified | DR090-01 Structures List
| Required | Hot Tap | Hot tap required? (Y or N) | DR100-01 Cable Schedule
| Required | Isometric Drawing | Piping isometric drawing number | DR120-01 Document Register
| Required | New | New line or equipment being tied in? (Y or N) | DR140-01 EWP Estimate
| Required | PID | Piping and instrumentation diagram drawing number | DR150-01 Material Requisition Tracking
| Required | Tie-In Type | Tie-in connection type (e.g., weld, flange, threaded, etc.) | DR170-01 Steel Detailing Deliverables
| Required | Sub-System ID | Unique turnover sub-system identifier | DR180-01 Steel Fabrication CWP Tracking
| Optional | Comments | Comment section | DR190-01 Pipe Isometric Detailing
| Optional | Plant Coordinate East | Plant coordinates east | DR200-01 Pipe CWP Fabrication Delivery Requirements
| Optional | Plant Coordinate Elevation | Plant coordinates elevation | DR230-01 Contractor Scope
| Optional | Plant Coordinate North | Plant coordinates north | DR260-01 Constraints
| Optional | Real World East | Real-world coordinates east | DR270-01 Materials Location
| Optional | Real World Elevation | Real-world coordinates elevation | DR290-01 Rules of Credit
| Optional | Real World North | Real-world coordinates north | DR310-01 Sub-Systems Index
| Optional | Tie-In Category | Gross connection category (e.g., module to module, module to stick built, etc.)

## DR070-04
AWP Piping Design
DR070-04 Pipe Support List
Key | Tier | Field Name | Definition | Directory
PK | Required | Project ID | Unique project identifier | DR000-01 Requirements List
PK | Required | Support Group ID | Unique identifier for pipe support | DR010-01 Project Information
PK | Required | Isometric Drawing | Piping Isometric drawing number | DR020-01 Schedule Activities
| Required | CWP | Unique construction work package identifier | DR050-01 Equipment List
| Required | Support Quantity | Quantity of support | DR070-01 Line List
| Required | Support Type | Type of support | DR080-01 Pipe Components
| Required | PO | Purchase order number | DR090-01 Structures List
| Optional | Support Description | Description of the support | DR100-01 Cable Schedule
| Optional | Support Size | Size of the pipe support (or size of item being supported) | DR120-01 Document Register
| Optional | Support Size UOM | Unit of measurement of pipe support size | DR140-01 EWP Estimate
| Optional | Support Tag | Unique tag number assigned to identify the project item | DR150-01 Material Requisition Tracking
DR170-01 Steel Detailing Deliverables
DR180-01 Steel Fabrication CWP Tracking
DR190-01 Pipe Isometric Detailing
DR200-01 Pipe CWP Fabrication Delivery Requirements
DR230-01 Contractor Scope
DR260-01 Constraints
DR270-01 Materials Location
DR290-01 Rules of Credit
DR310-01 Sub-Systems Index

## DR080-01
AWP 3D Modeling
DR080-01 Piping Components
Key | Tier | Field Name | Definition | Type (FR_TC_01) | Directory
PK | Required | Project ID | Unique project identifier | Organizational | DR000-01 Requirements List
PK | Required | Tag | Unique tag number assigned to identify a project item | Organizational | DR010-01 Project Information
| Required | Commodity Code | Commodity code | Technical | DR020-01 Schedule Activities
| Required | Type | Type of item (e.g., spool, weld, foundation, mechanical equipment, instrument, cable tray, etc.) | Technical | DR050-01 Equipment List
| Required | Construction Requirement | Specifies if it is new or existing and to be refurbished or modified | Organizational | DR070-01 Line List
| Required | CWA | Unique construction work area identifier | Organizational | DR080-01 Pipe Components
| Required | CWP | Unique construction work package identifier | Organizational | DR090-01 Structures List
| Required | EWP | Unique engineering work package identifier | Organizational | DR100-01 Cable Schedule
| Optional | Design System Path | Hierarchy placement of the model component in the design hierarchy or system breakdown structure (SBS) | Organizational | DR120-01 Document Register
| Required | Discipline | Discipline responsible for the engineering design | Organizational | DR140-01 EWP Estimate
| Optional | Fluid Code (Service) | Line service designation | Technical | DR150-01 Material Requisition Tracking
| Required | Isometric Drawing | Piping isometric drawing number | Organizational | DR170-01 Steel Detailing Deliverables
| Optional | Module | Module the component belongs to, when applicable | Organizational | DR180-01 Steel Fabrication CWP Tracking
| Optional | Length | Length of the item | Technical | DR190-01 Pipe Isometric Detailing
| Optional | Length UOM | Unit of measurement for length of the item (e.g., FT, M, etc.) | Technical | DR200-01 Pipe CWP Fabrication Delivery Requirements
| Optional | Weight | Weight of the item | Technical | DR230-01 Contractor Scope
| Optional | Weight UOM | Unit of measurement for weight of the item (e.g, TN, Lbs, MT, Kg, etc.) | Technical | DR260-01 Constraints
| Optional | Insulation Spec | Insulation specification of the item | Technical | DR270-01 Materials Location
| Optional | Insulation Thickness | Insulation thickness of the item | Technical | DR290-01 Rules of Credit
| Optional | Insulation Thickness UOM | Unit of measurement for insulation thickness (e.g., In, MM, etc.) | Technical | DR310-01 Sub-Systems Index
| Required | Line No. | Unique line number sequence | Organizational
| Optional | NPD - Size 1 | Nominal pipe diameter 1 – Pipe size at a first connection | Technical
| Optional | NPD - Size 2 | Nominal pipe diameter 2 – Pipe size at a second connection | Technical
| Optional | NPD - Size 3 | Nominal pipe diameter 3 – Pipe size at a third connection (for a tee) | Technical
| Optional | Pipe Components Description | Description of the item in the 3D design model | Technical
| Optional | Pressure Rating 1 | Pipe pressure rating 1 – at a first connection | Technical
| Optional | Pressure Rating 2 | Pipe pressure rating 2 – at a second connection | Technical
| Optional | Pressure Rating 3 | Pipe pressure rating 3 – at a third connection (three-way valve) | Technical
| Optional | Pressure Rating UOM | Unit of measurement for pressure rating (e.g., PSI, bar, Pa ) | Technical
| Optional | Temperature Rating 1 | Pipe temperature rating 1 - at a first connection | Technical
| Optional | Temperature Rating 2 | Pipe temperature rating 2 - at a second connection | Technical
| Optional | Temperature Rating 3 | Pipe temperature rating 3 - at a third connection (three-way valve) | Technical
| Optional | Temperature Rating UOM | Unit of measurement for temperature rating (e.g., F°, C°) | Technical
| Optional | Schedule 1 | Nominal pipe schedule 1 – Schedule or thickness of pipe at a first connection | Technical
| Optional | Schedule 2 | Nominal pipe schedule 2 – Schedule or thickness of pipe at a second connection | Technical
| Optional | Schedule 3 | Nominal pipe schedule 3 – Schedule or thickness of pipe at a third connection (for a tee) | Technical
| Optional | Shop / Field Flag | Indicates shop or field material | Technical
| Optional | Spec | Piping specification | Technical
| Optional | Tie-In ID | Unique tie-in identifier from engineering | Organizational
| Optional | Test Package ID | Unique test package identifier (e.g., hydrotest package) | Quality & Testing
| Optional | Train | Process train designation | Organizational
| Optional | Sub-System ID | Unique turnover sub-system identifier | Organizational
| Required | PID | Piping and instrumentation diagram drawing number | Organizational
| Required | Piping Material Type | Type of piping material | Technical
| Optional | Paint Code | Code that provides the paint color and mill thickness requirements | Technical
| Required | Weld Type | Type of weld | Technical
| Optional | Heat Trace | Heat trace | Technical
| Optional | Test Type | Type of test | Quality & Testing
| Optional | Inspection Test Plan | Inspection test plan | Quality & Testing
| Optional | From Tag | Tag number that this specific Tag is connected from | Technical
| Optional | To Tag | Tag number that this specific Tag is connected to | Technical

## DR080-02
AWP 3D Modeling
DR080-02 Generic Components
Key | Tier | Field Name | Definition | Type (FR_TC_01) | Directory
PK | Required | Project ID | Unique project identifier | Organizational | DR000-01 Requirements List
PK | Required | Tag | Unique tag number assigned to identify a project item | Organizational | DR010-01 Project Information
| Required | CWA | Unique construction work area identifier | Organizational | DR020-01 Schedule Activities
| Required | CWP | Unique construction work package identifier | Organizational | DR050-01 Equipment List
| Required | EWP | Unique engineering work package identifier | Organizational | DR070-01 Line List
| Required | Module | Module the tag belongs to, when applicable | Organizational | DR080-01 Pipe Components
| Required | Construction Requirement | Specifies whether it is new or existing and to be refurbished or modified | Organizational | DR090-01 Structures List
| Optional | Description | Description of the Tag function | Organizational | DR100-01 Cable Schedule
| Optional | Design System Path | Hierarchy placement of the model component in the design hierarchy or system breakdown structure (SBS) | Organizational | DR120-01 Document Register
| Optional | BOM Number | Bill of materials number | Organizational | DR140-01 EWP Estimate
| Required | Discipline | Discipline responsible for the engineering design | Organizational | DR150-01 Material Requisition Tracking
| Required | Type | Type of item (e.g., foundation, mechanical equipment, instrument, cable tray, etc.) | Technical | DR170-01 Steel Detailing Deliverables
| Required | Commodity Code | Commodity code | Technical | DR180-01 Steel Fabrication CWP Tracking
| Required | Qty | Key quantity of the item | Technical | DR190-01 Pipe Isometric Detailing
| Required | Qty UOM | Unit of measurement for key quantity of the item (e.g., FT, M, M3, PC) | Technical | DR200-01 Pipe CWP Fabrication Delivery Requirements
| Optional | Length | Length of the item | Technical | DR230-01 Contractor Scope
| Optional | Length UOM | Unit of measurement for length of the item (e.g., FT, M, etc.) | Technical | DR260-01 Constraints
| Optional | Width | Width of the item | Technical | DR270-01 Materials Location
| Optional | Width UOM | Unit of measurement for width of the item (e.g., FT, M, etc.) | Technical | DR290-01 Rules of Credit
| Optional | Height | Height of the item | Technical | DR310-01 Sub-Systems Index
| Optional | Height UOM | Unit of measurement for height of the item(e.g., FT, M, etc.) | Technical
| Optional | Weight | Weight of the item | Technical
| Optional | Weight UOM | Unit of measurement for weight of the item (e.g, TN, Lbs, Mt, Kg, etc.) | Technical
| Optional | Parent Tag | Parent tag associated to the item, if applicable | Organizational
| Optional | Tie-In ID | Unique tie-in identifier from engineering | Organizational
| Optional | Train | Process train designation | Organizational
| Optional | Sub-System ID | Unique turnover sub-system identifier | Organizational
| Optional | PID | Piping and instrumentation diagram drawing number | Organizational

## DR090-01
AWP Civil-Structural Design
DR090-01 Structures List
Key | Tier | Field Name | Definition | Directory
PK | Required | Project ID | Unique project identifier | DR000-01 Requirements List
PK | Required | Structure Tag | Unique tag number assigned to identify a project item | DR010-01 Project Information
| Required | Construction Requirement | Specifies whether it is new or existing and to be refurbished or modified | DR020-01 Schedule Activities
| Required | CWA | Unique construction work area identifier | DR050-01 Equipment List
| Required | CWP | Unique construction work package identifier | DR070-01 Line List
| Required | EWP | Unique engineering work package identifier | DR080-01 Pipe Components
| Required | Structure Description | Description of structure (e.g., cylinder purging, purging platform, etc.) | DR090-01 Structures List
| Required | Structure Type | Type of structure (e.g., building, process, rack, platform, MPS, etc.) | DR100-01 Cable Schedule
| Optional | Detailing Contract/PO | Detailing contract number or purchase order | DR120-01 Document Register
| Optional | Fabrication Contract/PO | Fabrication contract number or purchase order | DR140-01 EWP Estimate
| Optional | Structure Revision | Current revision | DR150-01 Material Requisition Tracking
DR170-01 Steel Detailing Deliverables
DR180-01 Steel Fabrication CWP Tracking
DR190-01 Pipe Isometric Detailing
DR200-01 Pipe CWP Fabrication Delivery Requirements
DR230-01 Contractor Scope
DR260-01 Constraints
DR270-01 Materials Location
DR290-01 Rules of Credit
DR310-01 Sub-Systems Index

## DR090-02
AWP Civil-Structural Design
DR090-02 Rebar
Key | Tier | Field Name | Definition | Directory
PK | Required | Project ID | Unique project identifier | DR000-01 Requirements List
PK | Required | Bar Mark | Mark of the bar | DR010-01 Project Information
PK | Required | Related Foundation Tag | Related foundation tag | DR020-01 Schedule Activities
| Required | Construction Requirement | Specifies whether it is new or existing and to be refurbished or modified | DR050-01 Equipment List
| Required | CWP | Unique construction work package identifier | DR070-01 Line List
| Required | Drawing Number | Location drawing number | DR080-01 Pipe Components
| Required | Bar Quantity | Quantity of rebar required | DR090-01 Structures List
| Required | Bar Quantity UOM | Unit of measurement for quantity of rebar required | DR100-01 Cable Schedule
| Required | Bar Diameter | Diameter of rebar required | DR120-01 Document Register
| Required | Bar Diameter UOM | Unit of measurement for diameter of rebar required | DR140-01 EWP Estimate
| Required | Bar Length | Length of rebar required | DR150-01 Material Requisition Tracking
| Required | Bar Length UOM | Unit of measurement for length of rebar required | DR170-01 Steel Detailing Deliverables
| Required | Bar Weight | Weight of rebar required | DR180-01 Steel Fabrication CWP Tracking
| Required | Bar Weight UOM | Unit of measurement for weight of rebar required | DR190-01 Pipe Isometric Detailing
| Required | Bar Type/Shape/Detail | Description of rebar required | DR200-01 Pipe CWP Fabrication Delivery Requirements
| Required | PO | Purchase order number | DR230-01 Contractor Scope
DR260-01 Constraints
DR270-01 Materials Location
DR290-01 Rules of Credit
DR310-01 Sub-Systems Index

## DR090-03
AWP Civil-Structural Design
DR090-03 Anchor Bolts
Key | Tier | Field Name | Definition | Directory
PK | Required | Project ID | Unique project identifier | DR000-01 Requirements List
PK | Required | Structure Tag | Unique tag number assigned to identify a project item | DR010-01 Project Information
PK | Required | Anchor Bolt ID | Unique identifier of the anchor bolt | DR020-01 Schedule Activities
| Required | Construction Requirement | Specifies whether it is new or existing and to be refurbished or modified | DR050-01 Equipment List
| Required | CWP | Unique construction work package identifier | DR070-01 Line List
| Required | Drawing Number | Location drawing number | DR080-01 Pipe Components
| Required | Anchor Bolts | Type of anchor bolts required | DR090-01 Structures List
| Required | Bolt Dia | Diameter of bolts | DR100-01 Cable Schedule
| Required | Bolt Dia UOM | Unit of measurement for bolt diameter | DR120-01 Document Register
| Required | No. of Anchor Bolt | Number of anchor bolts required | DR140-01 EWP Estimate
| Required | Bolt Length | Length of bolts required | DR150-01 Material Requisition Tracking
| Required | Bolt Length UOM | Unit of measurement for bolt length | DR170-01 Steel Detailing Deliverables
| Required | Projection Length | Projection length | DR180-01 Steel Fabrication CWP Tracking
| Required | Projection Length UOM | Unit of measurement for projection length | DR190-01 Pipe Isometric Detailing
DR200-01 Pipe CWP Fabrication Delivery Requirements
DR230-01 Contractor Scope
DR260-01 Constraints
DR270-01 Materials Location
DR290-01 Rules of Credit
DR310-01 Sub-Systems Index

## DR090-04
AWP Civil-Structural Design
DR090-04 Foundations
Key | Tier | Field Name | Definition | Directory
PK | Required | Project ID | Unique project identifier | DR000-01 Requirements List
PK | Required | Foundation Tag | Unique tag number assigned to identify a project item | DR010-01 Project Information
| Required | Related Structure/Equipment Tag | Related structure or equipment tag | DR020-01 Schedule Activities
| Required | CWP | Unique construction work package identifier | DR050-01 Equipment List
| Required | Drawing Number | Location drawing number | DR070-01 Line List
| Required | Construction Requirement | Specifies whther it is new or existing and to be refurbished or modified | DR080-01 Pipe Components
| Required | Concrete Volume | Volume of concrete | DR090-01 Structures List
| Required | Concrete Volume UOM | Unit of measurement for the volume of concrete | DR100-01 Cable Schedule
| Required | Foundation Type | Type of foundation (e.g., foundation, pedestal, deck, elevated slab) | DR120-01 Document Register
| Required | Concrete Strength | Strength of the concrete | DR140-01 EWP Estimate
| Required | Concrete Strength UOM | Unit of measurement for the strength of the concrete | DR150-01 Material Requisition Tracking
DR170-01 Steel Detailing Deliverables
DR180-01 Steel Fabrication CWP Tracking
DR190-01 Pipe Isometric Detailing
DR200-01 Pipe CWP Fabrication Delivery Requirements
DR230-01 Contractor Scope
DR260-01 Constraints
DR270-01 Materials Location
DR290-01 Rules of Credit
DR310-01 Sub-Systems Index

## DR100-01
AWP Electrical & Instrumentation Design
DR100-01 Cable Schedule
Key | Tier | Field Name | Definition | Directory
PK | Required | Project ID | Unique project identifier | DR000-01 Requirements List
PK | Required | Cable Tag | Unique tag number assigned to identify a project item | DR010-01 Project Information
| Required | Description | Description of the Tag function | DR020-01 Schedule Activities
| Required | Cable Status | Progress status of cable writing/routing process (i.e. written, checked, routed, route checked, released to construction) | DR050-01 Equipment List
| Required | Cable Type | Gives the engineered description of the type of cable (e.g., controls, high voltage, etc.) | DR070-01 Line List
| Required | Color Code | Industry color code for cable | DR080-01 Pipe Components
| Required | Conductors Config | Configuration of the conductors within the cable (e.g., single conductor, pairs, etc.) | DR090-01 Structures List
| Required | Construction Requirement | Specifies if it is new or existing and to be refurbished or modified | DR100-01 Cable Schedule
| Required | Cable Route | List of cable tray, conduit, etc. that cable runs through | DR120-01 Document Register
| Required | CWA | Unique construction work area identifier | DR140-01 EWP Estimate
| Required | CWP | Unique construction work package identifier | DR150-01 Material Requisition Tracking
| Required | EWP | Unique engineering work package identifier | DR170-01 Steel Detailing Deliverables
| Required | Cable Schedule | Cable schedule document number | DR180-01 Steel Fabrication CWP Tracking
| Required | Cable Schedule Revision | Current revision | DR190-01 Pipe Isometric Detailing
| Required | Layout Drawing - From | Number of layout drawing where a user will be able to locate the “From Tag” | DR200-01 Pipe CWP Fabrication Delivery Requirements
| Required | Layout Dwg From Rev | Layout drawing – from revision | DR230-01 Contractor Scope
| Required | Layout Drawing - To | Number of layout drawing where a user will be able to locate the “To Tag” | DR260-01 Constraints
| Required | Layout Dwg To Rev | Layout drawing – to revision | DR270-01 Materials Location
| Required | Length Engineered | Estimated design length of the cable | DR290-01 Rules of Credit
| Required | Length Pull | Actual length of the cable | DR310-01 Sub-Systems Index
| Required | Length UOM | Unit of measurement for length of the cable (e.g., F, IN, M, etc.)
| Required | Number | Number of actual conductors/pairs/triads within the cable
| Optional | Shield | Shielding type (e.g., IS = inside shield and OS = outside shield)
| Required | Conductor Size | Size of the conductor
| Required | Size UOM | Unit of measurement for cable size (e.g., AWG/American wire gauge, metric mm, etc.)
| Required | Voltage Rating | Voltage rating of the cable’s jackets
| Required | From Equipment | Equipment tag that circuit originates from (e.g., junction box, etc.)
| Required | To Equipment | Equipment tag that circuit terminates at (e.g., pump, etc.)
| Required | From Equipment Termination Type | Type of connection for the “From Equipment” side (e.g., hard wire, plug and socket, etc.)
| Required | To Equipment Termination Type | Type of connection for the “To Equipment” side (e.g., hard wire, plug and socket, etc.)
| Optional | Discipline | Discipline responsible for the engineering design
| Optional | Comments | Any comments related to the cable from engineering
| Required | Cable Drum Number | Cable drum number
| Required | Cable Gland Size | Cable gland size
| Required | Cable Gland Size UOM | Unit of measurement for cable gland size
| Required | Cable Routing Drawings | Cable routing drawings
| Required | Cable Joint | Cable joint
| Required | Cable Installation Details | Cable installation details

## DR100-02
AWP Electrical & Instrumentation Design
DR100-02 Electrical Equipment
Key | Tier | Field Name | Definition | Directory
PK | Required | Project ID | Unique project identifier | DR000-01 Requirements List
PK | Required | Tag | Unique tag number assigned to identify a project item | DR010-01 Project Information
| Required | Description | Description of the Tag function | DR020-01 Schedule Activities
| Required | Tag Status | Which engineering phase the tag is in | DR050-01 Equipment List
| Required | Equipment Type | Type of equipment (e.g., motor, junction box, etc.) | DR070-01 Line List
| Required | CWA | Unique construction work area identifier | DR080-01 Pipe Components
| Required | CWP | Unique construction work package identifier | DR090-01 Structures List
| Required | EWP | Unique engineering work package identifier | DR100-01 Cable Schedule
| Required | Manufacturer | Manufacturer of tagged item | DR120-01 Document Register
| Optional | Supplier | Supplier of tagged item | DR140-01 EWP Estimate
| Required | Serial Number | Serial number of tagged item | DR150-01 Material Requisition Tracking
| Required | Catalog Number | Model number | DR170-01 Steel Detailing Deliverables
| Required | Equipment Layout Drawing | Equipment layout drawing | DR180-01 Steel Fabrication CWP Tracking
| Required | Equipment Layout Drawing Revision | Equipment layout drawing revision | DR190-01 Pipe Isometric Detailing
| Required | PO | Purchase order number | DR200-01 Pipe CWP Fabrication Delivery Requirements
| Required | Skid | Skid tag number the equipment is part of | DR230-01 Contractor Scope
| Required | Sub-System ID | Unique turnover sub-system identifier | DR260-01 Constraints
| Optional | Test Package ID | Unique test package identifier (e.g., hydrotest package) | DR270-01 Materials Location
| Optional | Equipment Location Plan | Number of location drawing (e.g., B01-xxxx-yyyyy) | DR290-01 Rules of Credit
| Optional | Weight | Weight of the item | DR310-01 Sub-Systems Index
| Optional | Weight UOM | Unit of measurement for item weight (e.g, TN, Lbs, MT, Kg, etc.)
| Required | Vendor Drawing | Vendor drawing
| Required | Vendor Drawing Revision | Vendor drawing revision
| Required | Equipment Standard Detail Drawing | Equipment standard detail drawing
| Required | Equipment Standard Detail Revision | Current revision of the equipment standard detail drawing

## DR100-03
AWP Electrical & Instrumentation Design
DR100-03 Instrument Index
Key | Tier | Field Name | Definition | Directory
PK | Required | Project ID | Unique project identifier | DR000-01 Requirements List
PK | Required | Tag | Unique tag number assigned to identify a project item | DR010-01 Project Information
| Required | Description | Description of the Tag function | DR020-01 Schedule Activities
| Required | Tag Status | Which engineering phase the tag is in | DR050-01 Equipment List
| Required | CWA | Unique construction work area identifier | DR070-01 Line List
| Required | CWP | Unique construction work package identifier | DR080-01 Pipe Components
| Required | EWP | Unique engineering work package Identifier | DR090-01 Structures List
| Required | IWP | Unique installation work package identifier | DR100-01 Cable Schedule
| Optional | Related Tag | Equipment or line number tag associated with the item | DR120-01 Document Register
| Optional | I/O Type | Input/output type | DR140-01 EWP Estimate
| Required | Instrument Type | Type of the instrument | DR150-01 Material Requisition Tracking
| Required | Tag Location | Location details of the instrument in the plant facility | DR170-01 Steel Detailing Deliverables
| Optional | Manufacturer | Manufacturer of tagged item | DR180-01 Steel Fabrication CWP Tracking
| Required | PID | Piping and instrumentation diagram drawing number | DR190-01 Pipe Isometric Detailing
| Optional | Instrument Revision | Revision number of instrument design | DR200-01 Pipe CWP Fabrication Delivery Requirements
| Required | PO | Purchase order number | DR230-01 Contractor Scope
| Optional | Requisition Number | Material requisition number for the item | DR260-01 Constraints
| Required | Service | Process service associated with the item | DR270-01 Materials Location
| Optional | Sub-System ID | Unique turnover sub-system identifier | DR290-01 Rules of Credit
| Optional | Test Package ID | Unique test package identifier (e.g., hydrotest package) | DR310-01 Sub-Systems Index
| Optional | Model Number | Manufacturer model number
| Optional | Remarks | Any remarks or notes
| Optional | Face to Face | For inline instruments
| Optional | Instrument Rating | Rating of the instrument
| Optional | Weight | Weight of the item
| Optional | Weight UOM | Unit of measurement for item weight (e.g, TN, Lbs, MT, Kg, etc.)
| Optional | Control System Type | Type of control system (e.g., SIS, BPCS)
| Optional | Instrument Range | Minimum and maximum
| Required | Data Sheet Number | Data sheet number
| Required | Data Sheet Number Revision | Data sheet number revision
| Required | Hook-up Drawing Number | Hook-up drawing number
| Required | Hook-up Drawing Number Revision | Hook-up drawing number revision
| Required | Installation Drawing Number | Installation drawing number
| Required | Installation Drawing Number Revision | Installation drawing number revision
| Required | Location Layout Drawing | Location layout drawing
| Required | Location Layout Drawing Revision | Location layout drawing revision

## DR100-04
AWP Electrical & Instrumentation Design
DR100-04 Conduit
Key | Tier | Field Name | Definition | Directory
PK | Required | Project ID | Unique project identifier | DR000-01 Requirements List
PK | Required | Tag | Unique tag number assigned to identify a project item | DR010-01 Project Information
| Required | Description | Description of the Tag function | DR020-01 Schedule Activities
| Required | Tag Status | Which engineering phase the tag is in | DR050-01 Equipment List
| Required | % Filled | Calculation showing the percentage of the tray/conduit that has been used | DR070-01 Line List
| Required | Construction Requirement | Specifies whether it is new or existing and to be refurbished or modified | DR080-01 Pipe Components
| Required | CWP | Unique construction work package identifier | DR090-01 Structures List
| Required | EWP | Unique engineering work package identifier | DR100-01 Cable Schedule
| Optional | Fitting Style | Fitting style of a conduit fitting (i.e., EMT, rigid, LR 90, LL 90, etc.) | DR120-01 Document Register
| Optional | Fitting Type | Fitting type of a conduit fitting (i.e., straight thread, tapered thread, etc.) | DR140-01 EWP Estimate
| Optional | Conduit Part No. | Manufacturer’s part number for the conduit | DR150-01 Material Requisition Tracking
| Optional | Manufacturer | Manufacturer of tagged item | DR170-01 Steel Detailing Deliverables
| Optional | From Tag | Tag number that the specific conduit is connected from | DR180-01 Steel Fabrication CWP Tracking
| Optional | To Tag | Tag number that the specific conduit is connected to | DR190-01 Pipe Isometric Detailing
| Required | Layout Dwg - Ref 1 | Number of layout drawing that shows the conduit | DR200-01 Pipe CWP Fabrication Delivery Requirements
| Required | Drawing Revision - Ref 1 | Revision of layout drawing 1 | DR230-01 Contractor Scope
| Optional | Layout Dwg - Ref 2 | Number of second layout drawing that shows the conduit | DR260-01 Constraints
| Optional | Drawing Revision - Ref 2 | Revision of layout drawing 2 | DR270-01 Materials Location
| Required | Length | Length of the item | DR290-01 Rules of Credit
| Required | Length UOM | Unit of measurement for length of the item | DR310-01 Sub-Systems Index
| Required | Nominal Diameter | Nominal diameter of a conduit
| Required | Diameter UOM | Unit of measurement for diameter of the item
| Required | Material Type | Type of material the conduit is made of (e.g., rigid metal, electro-metallic tubing, etc.)
| Optional | Max Conduit Filled % | Maximum percent fill the conduit is allowed under code
| Required | Voltage Type | Compatible voltages for circuits run in the conduit/tray (e.g., segregation level: control, instrument, low/medium/high voltage, etc.)

## DR100-05
AWP Electrical & Instrumentation Design
DR100-05 Cable Tray
Key | Tier | Field Name | Definition | Directory
PK | Required | Project ID | Unique project identifier | DR000-01 Requirements List
PK | Required | Tag | Unique tag number assigned to identify a project item | DR010-01 Project Information
| Required | Description | Description of the Tag function | DR020-01 Schedule Activities
| Required | Tag Status | Which engineering phase the tag is in | DR050-01 Equipment List
| Optional | % Filled | Calculation showing the percentage of the tray that has been used | DR070-01 Line List
| Required | Tray Type | Type of bottom of a tray (i.e., ladder, solid, etc.) | DR080-01 Pipe Components
| Required | Construction Requirement | Specifies whether it is new or existing and to be refurbished or modified | DR090-01 Structures List
| Required | Cover Type | Type of tray cover, if necessary | DR100-01 Cable Schedule
| Required | CWP | Unique construction work package identifier | DR120-01 Document Register
| Required | EWP | Unique engineering work package identifier | DR140-01 EWP Estimate
| Optional | Manufacturer | Manufacturer of tagged item | DR150-01 Material Requisition Tracking
| Optional | Tray Part Type | Type of tray piecemark (i.e., straight run, elbow, T, cross, etc.) | DR170-01 Steel Detailing Deliverables
| Optional | Tray Part No. | Manufacturer’s part number for the tray | DR180-01 Steel Fabrication CWP Tracking
| Optional | Style | Type of raceway that represents the tag (i.e., tray, snap track, etc.) | DR190-01 Pipe Isometric Detailing
| Optional | From Tag | Tag number that the specific tray is connected from | DR200-01 Pipe CWP Fabrication Delivery Requirements
| Optional | To Tag | Tag number that the specific tray is connected to | DR230-01 Contractor Scope
| Required | Layout Dwg - Ref 1 | Number of layout drawing that shows the conduit | DR260-01 Constraints
| Required | Drawing Revision - Ref 1 | Revision of layout drawing 1 | DR270-01 Materials Location
| Optional | Layout Dwg - Ref 2 | Number of second layout drawing that shows the conduit | DR290-01 Rules of Credit
| Optional | Drawing Revision - Ref 2 | Revision of layout drawing 2 | DR310-01 Sub-Systems Index
| Required | Length | Length of the item
| Required | Length UOM | Unit of measurement for length of the item
| Required | Siderail Depth | Depth of the side rail on a tray
| Required | Depth UOM | Unit of measurement for depth of the side rail
| Required | Width 1 | Width of a tray
| Required | Width 2 | Width of a tray if more than one is applicable
| Required | Width UOM | Unit of measurement for width of the item
| Required | Material Type | Material type of the tray
| Optional | Max Cable Tray Filled % | Maximum percent fill the tray is allowed under code
| Optional | Voltage Type | Compatible voltages for circuits run in the conduit/tray (e.g., segregation level: control, instrument, low/medium/high voltage, etc.)

## DR100-06
AWP Electrical & Instrumentation Design
DR100-06 Lighting & Devices
Key | Tier | Field Name | Definition | Directory
PK | Required | Project ID | Unique project identifier | DR000-01 Requirements List
PK | Required | Tag | Unique tag number assigned to identify a project item | DR010-01 Project Information
| Required | Description | Description of the Tag function | DR020-01 Schedule Activities
| Required | Item Type | Accessories type (e.g., light receptacle, junction box, etc.) | DR050-01 Equipment List
| Required | Cable Size | Cable size | DR070-01 Line List
| Required | Circuit Number | Number of the circuit feeding lights and/or device | DR080-01 Pipe Components
| Required | Construction Requirement | Specifies whether it is new or existing and to be refurbished or modified | DR090-01 Structures List
| Required | CWP | Unique construction work package identifier | DR100-01 Cable Schedule
| Required | EWP | Unique engineering work package identifier | DR120-01 Document Register
| Optional | Manufacturer | Manufacturer of tagged item | DR140-01 EWP Estimate
| Optional | Supplier | Supplier of tagged item | DR150-01 Material Requisition Tracking
| Optional | Catalog Number | Catalog number | DR170-01 Steel Detailing Deliverables
| Optional | Mounting Style | Mounting style | DR180-01 Steel Fabrication CWP Tracking
| Optional | Operating Current Amp | Operating current amperage | DR190-01 Pipe Isometric Detailing
| Optional | Panel Name Tag | Engineered tag of panel feeding light and or receptacle | DR200-01 Pipe CWP Fabrication Delivery Requirements
| Optional | Terminals | Location and number of wire terminals | DR230-01 Contractor Scope
| Required | Panel Schedule | Panel schedule wiring drawing reference | DR260-01 Constraints
| Required | Panel Schedule Revision | Revision of equipment design | DR270-01 Materials Location
| Required | Drawing Number | Drawing number of lighting or device | DR290-01 Rules of Credit
| Required | Equipment Revision | Current revision of equipment | DR310-01 Sub-Systems Index
| Required | Standard Detail | Standard installation detail drawing reference for light and/or receptacle
| Required | Standard Detail Revision | Revision of equipment design
| Required | Test Package ID | Unique test package identifier
| Required | Voltage | Voltage in operation
| Required | Power | Wattage in operation
| Required | Usage | Type (e.g., emergency, general, etc.)
| Required | Single Line Diagram | Single line diagram
| Required | Single Line Diagram Revision | Revision of the single line diagram

## DR100-07
AWP Electrical & Instrumentation Design
DR100-07 Electrical Heat Tracing
Key | Tier | Field Name | Definition | Directory
PK | Required | Project ID | Unique project identifier | DR000-01 Requirements List
PK | Required | Tag | Unique tag number assigned to identify a project item | DR010-01 Project Information
| Required | Heat Trace Description | EHT circuit description | DR020-01 Schedule Activities
| Required | Manufacturer | Manufacturer of tagged item | DR050-01 Equipment List
| Optional | Catalog Part Number | EHT cable manufacturer part number | DR070-01 Line List
| Required | Construction Requirement | Specifies whther it is new or existing and to be refurbished or modified | DR080-01 Pipe Components
| Required | CWA | Unique construction work area identifier | DR090-01 Structures List
| Required | CWP | Unique construction work package identifier | DR100-01 Cable Schedule
| Required | EWP | Unique engineering work package identifier | DR120-01 Document Register
| Required | Length | Length of the item | DR140-01 EWP Estimate
| Required | Length UOM | Unit of measurement for length of the item | DR150-01 Material Requisition Tracking
| Required | From Tag (power) | Tag of a panel the circuit is connected from | DR170-01 Steel Detailing Deliverables
| Required | To Tag (customer) | Tag of equipment or piping line number the circuit is connected to | DR180-01 Steel Fabrication CWP Tracking
| Required | Typical Detail Drawing | Drawing of the EHT components used for the circuit | DR190-01 Pipe Isometric Detailing
| Optional | Equipment Revision | Current revision of the EHT tag | DR200-01 Pipe CWP Fabrication Delivery Requirements
| Optional | Control Type | Type of protection this circuit protects against (i.e., freezing, process control, etc.) | DR230-01 Contractor Scope
| Optional | Cable Rating | Classification rating of the cable (e.g., Class 1 Division 2, etc.) | DR260-01 Constraints
| Optional | Cable Joint | Cable joint | DR270-01 Materials Location
DR290-01 Rules of Credit
DR310-01 Sub-Systems Index

## DR120-01
AWP Document Control
DR120-01 Document Register
Key | Tier | Field Name | Definition | Directory
PK | Required | Project ID | Unique project identifier | DR000-01 Requirements List
PK | Required | Document Repository | Document repository identifier | DR010-01 Project Information
PK | Required | Document Number | Document number | DR020-01 Schedule Activities
PK | Required | Version Number | Controlled version number | DR050-01 Equipment List
PK | Required | Revision Number | Revision number of document | DR070-01 Line List
| Required | Document Discipline | Document discipline codes (which discipline this document comes from) | DR080-01 Pipe Components
| Required | Document File Name | Document filename (allows access to the file) | DR090-01 Structures List
| Required | Document File Type | Document type (e.g., PDF, DOC, etc.) | DR100-01 Cable Schedule
| Required | Document Status | Document status values (e.g., IFD, IFA, IFC) | DR120-01 Document Register
| Required | Document Title | Document title | DR140-01 EWP Estimate
| Required | Document Type | Document type (e.g., P&ID, arrangement, wiring diagram, data sheet, etc.) | DR150-01 Material Requisition Tracking
| Required | Revision Date | Revision date | DR170-01 Steel Detailing Deliverables
| Required | Transmittal Date | Receiving transmittal date | DR180-01 Steel Fabrication CWP Tracking
| Required | Transmittal Number | Receiving transmittal number | DR190-01 Pipe Isometric Detailing
| Required | Vendor Document Number | Vendor’s document number | DR200-01 Pipe CWP Fabrication Delivery Requirements
| Required | Vendor Revision | Vendor’s document revision number | DR230-01 Contractor Scope
| Required | Vendor Revision Date | Vendor’s revision date | DR260-01 Constraints
| Optional | Remarks | Any remarks or notes | DR270-01 Materials Location
DR290-01 Rules of Credit
DR310-01 Sub-Systems Index

## DR120-02
AWP Document Control
DR120-02 Document to Entity
Key | Tier | Field Name | Definition | Directory
PK | Required | Project ID | Unique project identifier | DR000-01 Requirements List
PK | Required | Document Number | Unique document identifier | DR010-01 Project Information
PK | Required | Relationship Type | Type of related ID (e.g., EWP, CWP, equipment tag, PO, system, etc.) | DR020-01 Schedule Activities
PK | Required | Related Tag | Unique identifier of the related entity | DR050-01 Equipment List
DR070-01 Line List
DR080-01 Pipe Components
DR090-01 Structures List
DR100-01 Cable Schedule
DR120-01 Document Register
DR140-01 EWP Estimate
DR150-01 Material Requisition Tracking
DR170-01 Steel Detailing Deliverables
DR180-01 Steel Fabrication CWP Tracking
DR190-01 Pipe Isometric Detailing
DR200-01 Pipe CWP Fabrication Delivery Requirements
DR230-01 Contractor Scope
DR260-01 Constraints
DR270-01 Materials Location
DR290-01 Rules of Credit
DR310-01 Sub-Systems Index

## DR140-01
AWP Estimating and Cost
DR140-01 EWP Estimate
Key | Tier | Field Name | Definition | Directory
PK | Required | Project ID | Unique project identifier | DR000-01 Requirements List
PK | Required | EWP | Unique engineering work package identifier | DR010-01 Project Information
| Required | Actual Expended Hours | Actual expended hours | DR020-01 Schedule Activities
| Required | Control Budget Hours | Construction hours allotted to the EWP per the control budget | DR050-01 Equipment List
| Required | Key Quantity | Sum total of key quantity for the EWP (e.g., 1000) | DR070-01 Line List
| Required | Key Quantity UOM | Unit of measurement for the key quantity (e.g., LF of pipe, etc.) | DR080-01 Pipe Components
| Optional | Actual Expended Cost | Actual expended cost | DR090-01 Structures List
| Optional | Total Estimated Cost | Total estimated construction cost of the EWP | DR100-01 Cable Schedule
DR120-01 Document Register
DR140-01 EWP Estimate
DR150-01 Material Requisition Tracking
DR170-01 Steel Detailing Deliverables
DR180-01 Steel Fabrication CWP Tracking
DR190-01 Pipe Isometric Detailing
DR200-01 Pipe CWP Fabrication Delivery Requirements
DR230-01 Contractor Scope
DR260-01 Constraints
DR270-01 Materials Location
DR290-01 Rules of Credit
DR310-01 Sub-Systems Index

## DR140-02
AWP Estimating and Cost
DR140-02 CWP Estimate
Key | Tier | Field Name | Definition | Directory
PK | Required | Project ID | Unique project identifier | DR000-01 Requirements List
PK | Required | CWP | Unique construction work package identifier | DR010-01 Project Information
| Required | Actual Expended Hours | Actual expended hours | DR020-01 Schedule Activities
| Required | Control Budget Hours | Construction hours allotted to the CWP per the control budget | DR050-01 Equipment List
| Required | Key Quantity | Sum total of key quantity for the CWP (e.g., 1000) | DR070-01 Line List
| Required | Key Quantity UOM | Unit of measurement for the key quantity (e.g., LF of pipe, etc.) | DR080-01 Pipe Components
| Optional | Actual Expended Cost | Actual expended cost | DR090-01 Structures List
| Optional | Total Estimated Cost | Total estimated construction cost of the CWP | DR100-01 Cable Schedule
DR120-01 Document Register
DR140-01 EWP Estimate
DR150-01 Material Requisition Tracking
DR170-01 Steel Detailing Deliverables
DR180-01 Steel Fabrication CWP Tracking
DR190-01 Pipe Isometric Detailing
DR200-01 Pipe CWP Fabrication Delivery Requirements
DR230-01 Contractor Scope
DR260-01 Constraints
DR270-01 Materials Location
DR290-01 Rules of Credit
DR310-01 Sub-Systems Index

## DR150-01
AWP Procurement
DR150-01 Material Requisition Tracking
Key | Tier | Field Name | Definition | Directory
PK | Required | Project ID | Unique project identifier | DR000-01 Requirements List
PK | Required | Requisition Number | Material requisition identifier | DR010-01 Project Information
| Optional | Requisition Description | Description of the requisition | DR020-01 Schedule Activities
| Optional | Requisition - Actual | Actual date to complete material requisition request | DR050-01 Equipment List
| Optional | Requisition - Forecast | Forecast date to material requisition request | DR070-01 Line List
| Optional | Requisition - Plan | Planned date to complete material requisition request | DR080-01 Pipe Components
| Optional | Inquiry - Actual | Actual date to complete vendor inquiries | DR090-01 Structures List
| Optional | Inquiry - Forecast | Forecast date to complete vendor inquiries | DR100-01 Cable Schedule
| Optional | Inquiry - Plan | Planned date to complete vendor inquiries | DR120-01 Document Register
| Optional | CBE - Actual | Actual date to complete commercial bid evaluation | DR140-01 EWP Estimate
| Optional | CBE - Forecast | Forecast date to complete commercial bid evaluation | DR150-01 Material Requisition Tracking
| Optional | CBE - Plan | Planned date to complete commercial bid evaluation | DR170-01 Steel Detailing Deliverables
| Optional | TBE - Actual | Actual date to complete technical bid evaluation | DR180-01 Steel Fabrication CWP Tracking
| Optional | TBE - Forecast | Forecast date to complete technical bid evaluation | DR190-01 Pipe Isometric Detailing
| Optional | TBE - Plan | Planned date to complete technical bid evaluation | DR200-01 Pipe CWP Fabrication Delivery Requirements
| Optional | Purchasing Agent | Group or division making purchase | DR230-01 Contractor Scope
| Required | Vendor | Vendor name | DR260-01 Constraints
| Required | Vendor ID | Unique vendor identifier | DR270-01 Materials Location
| Required | PO | Purchase order number | DR290-01 Rules of Credit
| Required | PO Description | Purchase order description | DR310-01 Sub-Systems Index
| Required | PO Status | Status of the PO (e.g., draft, issued)
| Required | PO Revision | Current revision of the PO
| Required | PO Date | Purchase order date (i.e., PO is cut)
| Optional | Incoterm | Applicable predefined international commercial terms as published by the International Chamber of Commerce (e.g., DDP, FCA)
| Optional | Requisition By | Team member
| Optional | Unit Price | Unit price
| Optional | Unit Price Currency | Unit price currency (USD, CAD)

## DR150-02
AWP Procurement
DR150-02 Purchase Order Line Items
Key | Tier | Field Name | Definition | Directory
PK | Required | Project ID | Unique project identifier | DR000-01 Requirements List
PK | Required | PO | Purchase order number | DR010-01 Project Information
PK | Required | Requisition Line Item | Line item on the requisition | DR020-01 Schedule Activities
PK | Required | Line Item Revision | Current revision of the line item | DR050-01 Equipment List
| Optional | Approve to Fab - Actual | Actual date for approval to fabricate | DR070-01 Line List
| Optional | Approve to Fab - Forecast | Forecast date for approval to fabricate | DR080-01 Pipe Components
| Optional | Approve to Fab - Plan | Planned date for approval to fabricate | DR090-01 Structures List
| Optional | Approve to Ship - Actual | Actual date for approval to ship | DR100-01 Cable Schedule
| Optional | Approve to Ship - Forecast | Forecast date for approval to ship | DR120-01 Document Register
| Optional | Approve to Ship - Plan | Planned date for approval to ship | DR140-01 EWP Estimate
| Required | BOM Description | Bill of materials description | DR150-01 Material Requisition Tracking
| Required | BOM ID | Materials identification code or stock code | DR170-01 Steel Detailing Deliverables
| Required | CWP | Unique construction work package identifier | DR180-01 Steel Fabrication CWP Tracking
| Required | Discipline | Discipline responsible for the engineering design | DR190-01 Pipe Isometric Detailing
| Required | ROS Date | Required on-site date for the needed quantity | DR200-01 Pipe CWP Fabrication Delivery Requirements
| Required | Material Category | Material category | DR230-01 Contractor Scope
| Required | Material Type | Material type within the category | DR260-01 Constraints
| Required | Qty PO | Quantity purchased | DR270-01 Materials Location
| Required | Qty UOM | Unit of measurement for quantity purchased (e.g., EA, LF, M, etc. ) | DR290-01 Rules of Credit
| Required | Tag | Unique tag number assigned to identify a project item | DR310-01 Sub-Systems Index
| Required | Vendor Drawings - Actual | Actual date of receiving vendor drawings
| Required | Vendor Drawings - Forecast | Forecast date of receiving vendor drawings
| Required | Vendor Drawings - Plan | Planned date of receiving vendor drawings
| Optional | Size | Material sizing information
| Optional | Size UOM | Unit of measurement for material sizing (e.g., EA, LF, M, etc.)

## DR150-03
AWP Procurement
DR150-03 Supplier Purchase Order Shipments
Key | Tier | Field Name | Definition | Directory
PK | Required | Project ID | Unique project identifier | DR000-01 Requirements List
PK | Required | Shipment ID | Shipment identifier | DR010-01 Project Information
PK | Required | PO | Purchase order number | DR020-01 Schedule Activities
PK | Required | PO Line Item | Line item on the purchase order | DR050-01 Equipment List
| Required | Material ID | Material identifier code | DR070-01 Line List
| Required | CWP | Unique construction work package identifier | DR080-01 Pipe Components
| Optional | ETA Refresh Date | Date when ETA information was updated from the supplier | DR090-01 Structures List
| Required | Date Ship – Actual | Actual date to ship in shipment lot | DR100-01 Cable Schedule
| Required | Date Ship – Forecast | Forecast date to ship in shipment lot | DR120-01 Document Register
| Required | Date Ship – Plan | Planned date to ship in shipment lot | DR140-01 EWP Estimate
| Required | Date Delivered – Actual | Actual date delivered | DR150-01 Material Requisition Tracking
| Required | Date Delivered – Forecast | Forecast delivery date | DR170-01 Steel Detailing Deliverables
| Required | Date Delivered – Plan | Planned delivery date | DR180-01 Steel Fabrication CWP Tracking
| Required | Discipline | Discipline responsible for the engineering design | DR190-01 Pipe Isometric Detailing
| Required | Material Category | Material category | DR200-01 Pipe CWP Fabrication Delivery Requirements
| Required | Material Type | Material type within the category | DR230-01 Contractor Scope
| Required | Qty Line Item | Quantity purchased | DR260-01 Constraints
| Required | Qty Ship – Actual | Actual quantity to ship in shipment lot | DR270-01 Materials Location
| Required | Qty Ship – Forecast | Forecast quantity to ship in shipment lot | DR290-01 Rules of Credit
| Required | Qty Ship – Plan | Planned quantity to ship in shipment lot | DR310-01 Sub-Systems Index
| Required | Qty Received | Total quantity received
| Required | Qty UOM | Unit of measurement for total quantity received (e.g., EA, LF, M, etc. )
| Required | Size | Material sizing information
| Required | Size UOM | Unit of measurement for material sizing (e.g., EA, LF, M, IN, etc.)
| Required | Tag | Unique tag number assigned to identify a project item

## DR150-04
AWP Procurement
DR150-04 Supplier Load Detail
Key | Tier | Field Name | Definition | Directory
PK | Required | Project ID | Unique project identifier | DR000-01 Requirements List
PK | Required | Shipment ID | Shipment identifier | DR010-01 Project Information
PK | Required | Load List ID | Load list identifier | DR020-01 Schedule Activities
PK | Required | Container ID | Identifier of container, box, pallet, etc. | DR050-01 Equipment List
| Optional | ETA Refresh Date | Date when ETA information was updated from the supplier | DR070-01 Line List
| Required | Date Ship – Actual | Actual date to ship in shipment lot | DR080-01 Pipe Components
| Required | Date Ship – Forecast | Forecast date to ship in shipment lot | DR090-01 Structures List
| Required | Date Ship – Plan | Planned date to ship in shipment lot | DR100-01 Cable Schedule
| Required | Date Delivered – Actual | Actual date delivered | DR120-01 Document Register
| Required | Date Delivered – Forecast | Forecast delivery date | DR140-01 EWP Estimate
| Required | Date Delivered – Plan | Planned delivery date | DR150-01 Material Requisition Tracking
| Required | Discipline | Discipline responsible for the engineering design | DR170-01 Steel Detailing Deliverables
| Optional | CWP | Unique construction work package identifier | DR180-01 Steel Fabrication CWP Tracking
DR190-01 Pipe Isometric Detailing
DR200-01 Pipe CWP Fabrication Delivery Requirements
DR230-01 Contractor Scope
DR260-01 Constraints
DR270-01 Materials Location
DR290-01 Rules of Credit
DR310-01 Sub-Systems Index

## DR150-05
AWP Procurement
DR150-05 Supplier Container Detail
Key | Tier | Field Name | Definition | Directory
PK | Required | Project ID | Unique project identifier | DR000-01 Requirements List
PK | Required | Shipment ID | Shipment identifier | DR010-01 Project Information
PK | Required | Load List ID | Load list identifier | DR020-01 Schedule Activities
PK | Required | Container ID | Identifier of container, box, pallet, etc. | DR050-01 Equipment List
PK | Required | Material ID | Material identifier for the BOM item(s) (bulk) or unique tag identifier if applicable (e.g., tag, spool number, commodity, etc.) | DR070-01 Line List
| Required | Item Description | Material description | DR080-01 Pipe Components
| Required | Qty | Quantity of item | DR090-01 Structures List
| Required | Qty UOM | Unit of measurement for quantity (e.g., EA, LF, M, etc. ) | DR100-01 Cable Schedule
| Required | CWP | Unique construction work package identifier | DR120-01 Document Register
| Required | Discipline | Discipline responsible for the engineering design | DR140-01 EWP Estimate
| Required | Material Category | Material category | DR150-01 Material Requisition Tracking
| Required | Material Type | Material type within the category | DR170-01 Steel Detailing Deliverables
| Required | Qty Received | Total quantity received | DR180-01 Steel Fabrication CWP Tracking
| Optional | Size | Material sizing Information | DR190-01 Pipe Isometric Detailing
| Optional | Size UOM | Unit of measurement for material sizing | DR200-01 Pipe CWP Fabrication Delivery Requirements
| Optional | Weight | Weight of the item | DR230-01 Contractor Scope
| Optional | Weight UOM | Unit of measurement for weight (e.g, TN, Lbs, MT, Kg, etc.) | DR260-01 Constraints
DR270-01 Materials Location
DR290-01 Rules of Credit
DR310-01 Sub-Systems Index

## DR170-01
AWP Structural Detailing
DR170-01 Steel Detailing Deliverables
Key | Tier | Field Name | Definition | Directory
PK | Required | Project ID | Unique project identifier | DR000-01 Requirements List
PK | Required | Structure Tag | Unique tag number assigned to identify a project item | DR010-01 Project Information
| Required | CWP | Unique construction work package identifier | DR020-01 Schedule Activities
| Optional | Designs to Detailer - Actual | Actual date for the engineer to provide designs to detailing | DR050-01 Equipment List
| Optional | Designs to Detailer - Forecast | Forecasted date for the engineer to provide designs to detailing | DR070-01 Line List
| Optional | Designs to Detailer - Plan | Planned date for the engineer to provide designs to detailing | DR080-01 Pipe Components
| Optional | Detail File Name | Structural detail file name | DR090-01 Structures List
| Optional | Erection Dwgs from Detailer - Actual | Actual date for the tracking of delivery of steel erection from detailer | DR100-01 Cable Schedule
| Optional | Erection Dwgs from Detailer - Forecast | Forecasted date for the tracking of delivery of steel erection from detailer | DR120-01 Document Register
| Optional | Erection Dwgs from Detailer - Plan | Planned date for the tracking of delivery of steel erection from detailer | DR140-01 EWP Estimate
| Optional | Models from Detailer - Actual | Actual date for steel models and drawings to arrive from detailer | DR150-01 Material Requisition Tracking
| Optional | Models from Detailer - Forecast | Forecasted date for steel models and drawings to arrive from a detailer | DR170-01 Steel Detailing Deliverables
| Optional | Models from Detailer - Plan | Planned date for steel models and drawings to arrive from a detailer | DR180-01 Steel Fabrication CWP Tracking
| Optional | Structure Type | Type of structure (e.g., piperack, ladder, etc.) | DR190-01 Pipe Isometric Detailing
DR200-01 Pipe CWP Fabrication Delivery Requirements
DR230-01 Contractor Scope
DR260-01 Constraints
DR270-01 Materials Location
DR290-01 Rules of Credit
DR310-01 Sub-Systems Index

## DR170-02
AWP Structural Detailing
DR170-02 Steel Detail Drawings
Key | Tier | Field Name | Definition | Directory
PK | Required | Project ID | Unique project identifier | DR000-01 Requirements List
PK | Required | Drawing ID | Document number | DR010-01 Project Information
PK | Required | Revision Number | Revision number of the issued document | DR020-01 Schedule Activities
| Required | Structure Tag | Unique tag number assigned to identify a project item | DR050-01 Equipment List
| Required | Drawing Type | Drawing class (e.g., GA, erection drawing) | DR070-01 Line List
| Required | Drawing Filename | Drawing (PDF) filename | DR080-01 Pipe Components
| Optional | Sequence | Sequence of the steel drawing within the IWP (i.e. represents the path of construction) | DR090-01 Structures List
| Optional | Transmittal Date | Transmittal date | DR100-01 Cable Schedule
| Optional | Transmittal ID | Transmittal ID number | DR120-01 Document Register
DR140-01 EWP Estimate
DR150-01 Material Requisition Tracking
DR170-01 Steel Detailing Deliverables
DR180-01 Steel Fabrication CWP Tracking
DR190-01 Pipe Isometric Detailing
DR200-01 Pipe CWP Fabrication Delivery Requirements
DR230-01 Contractor Scope
DR260-01 Constraints
DR270-01 Materials Location
DR290-01 Rules of Credit
DR310-01 Sub-Systems Index

## DR170-03
AWP Structural Detailing
DR170-03 Steel Piecemarks
Key | Tier | Field Name | Definition | Directory
PK | Required | Project ID | Unique project identifier | DR000-01 Requirements List
PK | Required | Structure Tag | Unique tag number assigned to identify a project item | DR010-01 Project Information
PK | Required | Piecemark | Piecemark identifier | DR020-01 Schedule Activities
| Required | Count | Piece mark count | DR050-01 Equipment List
| Required | Structural Shape | Type of structural steel (e.g., W, angle, etc.) | DR070-01 Line List
| Required | Length | Length of the item | DR080-01 Pipe Components
| Required | Length UOM | Unit of measurement for length of the item (e.g., FT, M, etc.) | DR090-01 Structures List
| Required | Weight | Weight of the item | DR100-01 Cable Schedule
| Required | Weight UOM | Unit of measurement for weight of the item (e.g, TN, Lbs, Mt, Kg, etc.) | DR120-01 Document Register
DR140-01 EWP Estimate
DR150-01 Material Requisition Tracking
DR170-01 Steel Detailing Deliverables
DR180-01 Steel Fabrication CWP Tracking
DR190-01 Pipe Isometric Detailing
DR200-01 Pipe CWP Fabrication Delivery Requirements
DR230-01 Contractor Scope
DR260-01 Constraints
DR270-01 Materials Location
DR290-01 Rules of Credit
DR310-01 Sub-Systems Index

## DR170-04
AWP Structural Detailing
DR170-04 Steel 3D Model Relationship
Key | Tier | Field Name | Definition | Directory
PK | Required | Project ID | Unique project identifier | DR000-01 Requirements List
PK | Required | Global Unique Identifier | Global unique identifier (GUID) | DR010-01 Project Information
| Required | Piecemark | Assembly mark number | DR020-01 Schedule Activities
| Required | Erection Drawing ID | Unique identifier of the erection drawing | DR050-01 Equipment List
| Required | Drawing Name | Title of drawing (e.g., hot oil heater erection drawing) | DR070-01 Line List
| Optional | Count of Connections | Count of connections per piecemark assembly (e.g., a beam has two connections) | DR080-01 Pipe Components
DR090-01 Structures List
DR100-01 Cable Schedule
DR120-01 Document Register
DR140-01 EWP Estimate
DR150-01 Material Requisition Tracking
DR170-01 Steel Detailing Deliverables
DR180-01 Steel Fabrication CWP Tracking
DR190-01 Pipe Isometric Detailing
DR200-01 Pipe CWP Fabrication Delivery Requirements
DR230-01 Contractor Scope
DR260-01 Constraints
DR270-01 Materials Location
DR290-01 Rules of Credit
DR310-01 Sub-Systems Index

## DR170-05
AWP Structural Detailing
DR170-05 Steel Connection Details
Key | Tier | Field Name | Definition | Directory
PK | Required | Project ID | Unique project identifier | DR000-01 Requirements List
PK | Required | Piecemark | Assembly mark number | DR010-01 Project Information
PK | Required | Assembly Global ID | Assembly global identifier (Connection ID) | DR020-01 Schedule Activities
| Required | Bolt Acceptance Criteria | Method of acceptance for confirming fully installed (e.g., direct tension indicator [DTI], turn-of-nut, torsion, etc.) | DR050-01 Equipment List
| Required | Bolt Details | Bolt details, including diameter and length | DR070-01 Line List
| Required | Bolt Quantity | Quantity for the bolts | DR080-01 Pipe Components
| Required | Bolt Type | Bolt type, such as ASTM A325 (heavy hex structural steel bolts) | DR090-01 Structures List
| Optional | Connect To | Connect to assembly mark number | DR100-01 Cable Schedule
| Optional | Connection Type | Classification of the particular connection type (e.g., weld, bolt) | DR120-01 Document Register
| Optional | Weld Joint Designation Code | Welding joint code per AWS D1.1/D1.1M (e.g., B-P1A, butt weld / partial penetration joint [PPJ] / square groove weld / SMAW) | DR140-01 EWP Estimate
| Optional | Weld Joint Thickness | Thickness of the steel to be welded | DR150-01 Material Requisition Tracking
| Optional | Thickness UOM | Unit of measurement for weld joint thickness (e.g., FT, M, IN, etc.) | DR170-01 Steel Detailing Deliverables
| Optional | Weld Quantity | Linear inches of weld | DR180-01 Steel Fabrication CWP Tracking
| Optional | Weld Type | Specific welding machine/method used for this connection (e.g., SMAW, FCAW, GMAW, etc.) | DR190-01 Pipe Isometric Detailing
DR200-01 Pipe CWP Fabrication Delivery Requirements
DR230-01 Contractor Scope
DR260-01 Constraints
DR270-01 Materials Location
DR290-01 Rules of Credit
DR310-01 Sub-Systems Index

## DR180-01
AWP Steel Fabrication
DR180-01 Steel Fabrication CWP Tracking
Key | Tier | Field Name | Definition | Directory
PK | Required | Project ID | Unique project identifier | DR000-01 Requirements List
PK | Required | Fabrication Scope | Unique scope identifier (e.g., PWP, fabrication contract/PO, etc.) | DR010-01 Project Information
PK | Required | CWP | Unique construction work package identifier | DR020-01 Schedule Activities
| Optional | Drawings To Shop Complete - Actual | Actual date for the complete drawings to reach the shop | DR050-01 Equipment List
| Optional | Drawings To Shop Complete - Forecast | Forecast date for the complete drawings to reach the shop | DR070-01 Line List
| Optional | Drawings To Shop Complete - Plan | Planned date for the complete drawings to reach the shop | DR080-01 Pipe Components
| Optional | Fabrication Complete - Actual | Actual date for fabrication to be complete | DR090-01 Structures List
| Optional | Fabrication Complete - Forecast | Forecast date for fabrication to be complete | DR100-01 Cable Schedule
| Optional | Fabrication Complete - Plan | Planned date for fabrication to be complete | DR120-01 Document Register
| Optional | Fabrication Percent Complete | Fabrication completeness as a percentage | DR140-01 EWP Estimate
| Optional | Shipment Complete - Actual | Actual date for shipment to be complete | DR150-01 Material Requisition Tracking
| Optional | Shipment Complete - Forecast | Forecast date for shipment to be complete | DR170-01 Steel Detailing Deliverables
| Optional | Shipment Complete - Plan | Planned date for shipment to be complete | DR180-01 Steel Fabrication CWP Tracking
| Optional | Shipping Percent Complete | Percentage of shipment complete by piecemark count | DR190-01 Pipe Isometric Detailing
| Optional | CWP Steel Delivery - Actual | Actual date to deliver all steel for the CWP | DR200-01 Pipe CWP Fabrication Delivery Requirements
| Optional | CWP Steel Delivery - Forecast | Forecast date to deliver all steel for the CWP | DR230-01 Contractor Scope
| Optional | CWP Steel Delivery - Plan | Planned date to deliver all steel for the CWP | DR260-01 Constraints
| Optional | CWP Steel Delivery - ROS | Required on-site date specified for the CWP | DR270-01 Materials Location
| Optional | Detailer | Name of the detailer (company name) | DR290-01 Rules of Credit
| Optional | Specialty Coating Complete - Actual | Actual date for specialty coating to be complete | DR310-01 Sub-Systems Index
| Optional | Specialty Coating Complete - Forecast | Forecast date for specialty coating to be complete
| Optional | Specialty Coating Complete - Plan | Planned date for specialty coating to be complete
| Optional | CWP Weight | Actual weight of the CWP
| Optional | Weight UOM | Unit of measurement for weight of the CWP (e.g, TN, Lbs, Mt, Kg, etc.)

## DR180-02
AWP Steel Fabrication
DR180-02 Steel Fabrication Details Tracking
Key | Tier | Field Name | Definition | Directory
PK | Required | Project ID | Unique project identifier | DR000-01 Requirements List
PK | Required | CWP | Unique construction work package identifier | DR010-01 Project Information
PK | Required | Piecemark | Assembly mark number | DR020-01 Schedule Activities
| Required | Structure Tag | Unique tag number assigned to identify a project item | DR050-01 Equipment List
| Required | Member Type | Piece mark member type (i.e. beam, column, brace, etc.) | DR070-01 Line List
| Required | Count Fabricated | Piece mark count fabricated | DR080-01 Pipe Components
| Required | Count Required | Piece mark count required | DR090-01 Structures List
| Required | Count Shipped | Piece mark count shipped | DR100-01 Cable Schedule
| Required | Length | Length of the item | DR120-01 Document Register
| Required | Length UOM | Unit of measurement for length of the item (e.g., FT, M, etc.) | DR140-01 EWP Estimate
| Required | Weight | Weight of the item | DR150-01 Material Requisition Tracking
| Required | Weight UOM | Unit of measurement for weight of the item (e.g., TN, Lbs, Mt, Kg, etc.) | DR170-01 Steel Detailing Deliverables
| Optional | 3D GUID | A comma-separated list of 3D model piecemark GUIDs within CWP | DR180-01 Steel Fabrication CWP Tracking
| Optional | Galvanizing Required | Indicates whether structure requires galvanizing | DR190-01 Pipe Isometric Detailing
| Optional | Fireproofing Required | Indicates whether structure requires fireproofing | DR200-01 Pipe CWP Fabrication Delivery Requirements
DR230-01 Contractor Scope
DR260-01 Constraints
DR270-01 Materials Location
DR290-01 Rules of Credit
DR310-01 Sub-Systems Index

## DR190-01
AWP Pipe Detailing
DR190-01 Pipe Isometric Detailing
Key | Tier | Field Name | Definition | Directory
PK | Required | Project ID | Unique project identifier | DR000-01 Requirements List
PK | Required | Isometric Drawing | Piping isometric drawing number | DR010-01 Project Information
| Required | CWP | Unique construction work package identifier | DR020-01 Schedule Activities
| Optional | Engineering Isos to Detailer - Actual | Actual date for engineer to transmit pipe isometrics | DR050-01 Equipment List
| Optional | Engineering Isos to Detailer - Forecast | Forecast date for engineer to transmit pipe isometrics | DR070-01 Line List
| Optional | Engineering Isos to Detailer - Plan | Planned date for engineer to transmit pipe isometrics | DR080-01 Pipe Components
| Optional | Fabricator Detailing Delivery - Actual | Actual date for delivery of pipe drawings from a detailer | DR090-01 Structures List
| Optional | Fabricator Detailing Delivery - Forecast | Forecast date for delivery of pipe drawings from a detailer | DR100-01 Cable Schedule
| Optional | Fabricator Detailing Delivery - Plan | Planned date for delivery of pipe drawings from a detailer | DR120-01 Document Register
| Optional | Piping Line Number | Parent line number of associated isometric | DR140-01 EWP Estimate
DR150-01 Material Requisition Tracking
DR170-01 Steel Detailing Deliverables
DR180-01 Steel Fabrication CWP Tracking
DR190-01 Pipe Isometric Detailing
DR200-01 Pipe CWP Fabrication Delivery Requirements
DR230-01 Contractor Scope
DR260-01 Constraints
DR270-01 Materials Location
DR290-01 Rules of Credit
DR310-01 Sub-Systems Index

## DR190-02
AWP Pipe Detailing
DR190-02 Pipe Isometric Transmittals
Key | Tier | Field Name | Definition | Directory
PK | Required | Project ID | Unique project identifier | DR000-01 Requirements List
PK | Required | Isometric Drawing | Piping isometric drawing number | DR010-01 Project Information
PK | Required | Isometric File Type | File type of isometric (e.g., PDF, PCF, etc.) | DR020-01 Schedule Activities
PK | Required | Transmittal ID | Transmittal ID the document was issued under | DR050-01 Equipment List
| Required | Isometric Revision | Pipe isometric’s revision released version | DR070-01 Line List
| Required | Doc Status | Current state of release of the pipe isometric ( i.e., IFA, IFC) | DR080-01 Pipe Components
| Required | CWP | Unique construction work package identifier | DR090-01 Structures List
| Required | On Hold | Indicates whether the isometric is currently on hold | DR100-01 Cable Schedule
| Required | Deleted | Indicates whether the ISO has been deleted | DR120-01 Document Register
| Required | Isometric File Name | Name of isometric (includes extension) | DR140-01 EWP Estimate
| Optional | Isometric File Title | Title of isometric | DR150-01 Material Requisition Tracking
DR170-01 Steel Detailing Deliverables
DR180-01 Steel Fabrication CWP Tracking
DR190-01 Pipe Isometric Detailing
DR200-01 Pipe CWP Fabrication Delivery Requirements
DR230-01 Contractor Scope
DR260-01 Constraints
DR270-01 Materials Location
DR290-01 Rules of Credit
DR310-01 Sub-Systems Index

## DR190-03
AWP Pipe Detailing
DR190-03 Pipe Spools
Key | Tier | Field Name | Definition | Directory
PK | Required | Project ID | Unique project identifier | DR000-01 Requirements List
PK | Required | Spool Tag | Pipe spool unique identifier | DR010-01 Project Information
| Required | Isometric Drawing | Piping isometric drawing number | DR020-01 Schedule Activities
| Required | CWP | Unique construction work package identifier | DR050-01 Equipment List
| Required | Length | Length of the item | DR070-01 Line List
| Required | Length UOM | Unit of measurement for length of the item (e.g., FT, M, etc.) | DR080-01 Pipe Components
| Required | Material | Spool material of construction | DR090-01 Structures List
| Required | Weight | Weight of the item | DR100-01 Cable Schedule
| Required | Weight UOM | Unit of measurement for weight of the item (e.g, TN, Lbs, Mt, Kg, etc.) | DR120-01 Document Register
| Required | Schedule/Thickness | Spool schedule or wall thickness | DR140-01 EWP Estimate
DR150-01 Material Requisition Tracking
DR170-01 Steel Detailing Deliverables
DR180-01 Steel Fabrication CWP Tracking
DR190-01 Pipe Isometric Detailing
DR200-01 Pipe CWP Fabrication Delivery Requirements
DR230-01 Contractor Scope
DR260-01 Constraints
DR270-01 Materials Location
DR290-01 Rules of Credit
DR310-01 Sub-Systems Index

## DR200-01
AWP Pipe Fabrication
DR200-01 Pipe CWP Fabrication Delivery Requirements
Key | Tier | Field Name | Definition | Directory
PK | Required | Project ID | Unique project identifier | DR000-01 Requirements List
PK | Required | Fabrication Scope | Unique scope identifier (e.g., PWP, fabrication contract/PO, etc.) | DR010-01 Project Information
PK | Required | CWP | Unique construction work package identifier | DR020-01 Schedule Activities
| Required | CWP Pipe Spools Delivery - ROS | Required on site date specified for the PWP | DR050-01 Equipment List
| Required | CWP Pipe Spools Delivery - Planned | Planned date to deliver all pipe spools for the CWP | DR070-01 Line List
| Required | CWP Pipe Spools Delivery - Forecast | Forecast date to deliver all pipe spools for the CWP | DR080-01 Pipe Components
| Optional | CWP Pipe Spools Delivery - Actual | Actual date to deliver all pipe spools for the CWP | DR090-01 Structures List
DR100-01 Cable Schedule
DR120-01 Document Register
DR140-01 EWP Estimate
DR150-01 Material Requisition Tracking
DR170-01 Steel Detailing Deliverables
DR180-01 Steel Fabrication CWP Tracking
DR190-01 Pipe Isometric Detailing
DR200-01 Pipe CWP Fabrication Delivery Requirements
DR230-01 Contractor Scope
DR260-01 Constraints
DR270-01 Materials Location
DR290-01 Rules of Credit
DR310-01 Sub-Systems Index

## DR200-02
AWP Pipe Fabrication
DR200-02 Pipe Spool Fabrication Tracking
Key | Tier | Field Name | Definition | Directory
PK | Required | Project ID | Unique project identifier | DR000-01 Requirements List
PK | Required | Spool Tag | Unique tag number assigned to identify a project item | DR010-01 Project Information
| Required | CWP | Unique construction work package identifier | DR020-01 Schedule Activities
| Required | CWA | Costruction Work Area Identifier | DR050-01 Equipment List
| Required | EWP | Engineering Work Package | DR070-01 Line List
| Required | Isometric Drawing | Piping isometric drawing number | DR080-01 Pipe Components
| Required | In Production | Date the pipe spool fabrication began | DR090-01 Structures List
| Required | Fabrication Complete | Date the pipe spool fabrication was completed | DR100-01 Cable Schedule
| Optional | Painting Complete | Date the pipe spool painting was completed | DR120-01 Document Register
| Optional | PWHT Complete | Date the pipe spool had post weld heat treatment, if required | DR140-01 EWP Estimate
| Required | Length | Length of the item | DR150-01 Material Requisition Tracking
| Required | Length UOM | Unit of measurement for length of the item (e.g., FT, M, etc.) | DR170-01 Steel Detailing Deliverables
| Required | Weight | Weight of the item | DR180-01 Steel Fabrication CWP Tracking
| Required | Weight UOM | Unit of measurement for weight of the item (e.g, TN, Lbs, MT, Kg, etc.) | DR190-01 Pipe Isometric Detailing
| Optional | Material Allocated | Date spool material was allocated | DR200-01 Pipe CWP Fabrication Delivery Requirements
| Required | On Hold Date | Date engineering placed a hold on fabrication of the pipe spool | DR230-01 Contractor Scope
| Required | Release Hold | Date engineering released a hold on the spool | DR260-01 Constraints
| Required | ROS | Required onsite date for this pipe spool | DR270-01 Materials Location
| Optional | QA/QC Complete | Date QA/QC completed inspection | DR290-01 Rules of Credit
| Optional | Header Size | Maximum size of the header | DR310-01 Sub-Systems Index
| Optional | Priority | Project priority
| Optional | Transmittal No. | Transmittal number
| Optional | Material Type | Material type
| Optional | Material Type Description | Material type description
| Optional | Line Spec | Specification of the line
| Optional | Heat Treat | Heat treatment requirement
| Optional | Shop Test | Hydrotest or pneumatic requirement
| Optional | Surface Area | Surface area of the spool
| Optional | FDI | Field diameter inch
| Optional | Last Status | Last status numerical identifier
| Optional | Last Status Desc | Last status text identifier
| Optional | Next Status | Next status numerical identifier
| Optional | Next Status Desc | Next status text identifier
| Optional | Paint System | Paint code
| Optional | Released to Shop Date | Status date timestamp - released to shop
| Optional | Cut Complete Date | Status date timestamp - cut complete
| Optional | Weld Complete Date | Status date timestamp - weld complete
| Optional | QC Complete Date | Status date timestamp - quality control complete
| Optional | Ship Complete Date | Status date timestamp - shipping complete
| Optional | Delivery No. | Delivery number
| Optional | Ship To Name | Shipping name received
| Optional | Hold Code | Hold code
| Optional | Hold Date | Hold date timestamp
| Optional | Data Date | Current record data date
| Optional | Remarks | Any remarks or notes

## DR230-01
AWP Contractor Scope Items
DR230-01 Contractor Scope
Key | Tier | Field Name | Definition | Directory
PK | Required | Project ID | Unique project identifier | DR000-01 Requirements List
PK | Required | Contractor ID | Labor contractor on the project that performed the material take-off (MTO) for the CWP | DR010-01 Project Information
PK | Required | Scope Item | Item that may be from the construction contractor’s take-off or progress database, line items from an estimate, IFC drawings, schedule activities, installation work packages, or any other basis of defining scope | DR020-01 Schedule Activities
| Required | CWP | Unique construction work package identifier | DR050-01 Equipment List
| Required | IWP | Unique installation work package identifier | DR070-01 Line List
| Required | Discipline | Discipline responsible for the engineering design | DR080-01 Pipe Components
| Optional | Est Hrs | Estimated hours for installation activities associated with the reported quantities | DR090-01 Structures List
| Optional | Tag | Unique tag number assigned to identify a project item | DR100-01 Cable Schedule
| Optional | Test Package Designation | Test package identifier | DR120-01 Document Register
| Required | Scope Total QTY | Total quantity of the material type within the CWP for the primary and secondary classifications | DR140-01 EWP Estimate
| Required | Scope QTY UOM | Unit of measurement for the total quantity field (e.g., EA, LF, Dia. In, M) | DR150-01 Material Requisition Tracking
| Optional | Sub-System ID | Unique turnover sub-system identifier | DR170-01 Steel Detailing Deliverables
| Optional | Phase | Field phase of execution (e.g., construction, testing, etc.) | DR180-01 Steel Fabrication CWP Tracking
| Optional | Material Take-off Document Number | Document number of the material take-off | DR190-01 Pipe Isometric Detailing
| Optional | Material Description | Short description of the material in consideration for the MTO analysis | DR200-01 Pipe CWP Fabrication Delivery Requirements
| Optional | Material Type | Specific type of material within the scope of the CWP | DR230-01 Contractor Scope
DR260-01 Constraints
DR270-01 Materials Location
DR290-01 Rules of Credit
DR310-01 Sub-Systems Index

## DR260-01
AWP Constraints
DR260-01 Constraints
Key | Tier | Field Name | Definition | Directory
PK | Required | Project ID | Unique project identifier | DR000-01 Requirements List
PK | Required | Package ID | Unique package identified (e.g., the IWP or CWP number) | DR010-01 Project Information
PK | Required | Package Type | Type of package (IWP, CWP, STR, etc.) | DR020-01 Schedule Activities
PK | Required | Constraint ID | Unique constraint identifier within the package | DR050-01 Equipment List
| Required | Assigned To | Party responsible for clearing the constraint | DR070-01 Line List
| Required | Constraint Description | Specific description of the constraint | DR080-01 Pipe Components
| Required | Constraint Type | Type of constraint (e.g., materials, scaffold, manpower, etc.) | DR090-01 Structures List
| Required | Date Identified | Date the constraint was identified | DR100-01 Cable Schedule
| Required | Date Required | Date the constraint is due to be cleared | DR120-01 Document Register
| Required | Date Resolved | Date the constraint is resolved | DR140-01 EWP Estimate
| Required | Constraint Status | Current status (e.g., working, on-hold, cleared, etc.) | DR150-01 Material Requisition Tracking
| Optional | Notes | Miscellaneous notes | DR170-01 Steel Detailing Deliverables
DR180-01 Steel Fabrication CWP Tracking
DR190-01 Pipe Isometric Detailing
DR200-01 Pipe CWP Fabrication Delivery Requirements
DR230-01 Contractor Scope
DR260-01 Constraints
DR270-01 Materials Location
DR290-01 Rules of Credit
DR310-01 Sub-Systems Index

## DR270-01
AWP Site Materials
DR270-01 Materials Location
Key | Tier | Field Name | Definition | Directory
PK | Required | Project ID | Unique project identifier | DR000-01 Requirements List
PK | Required | Facility ID | Short identifier to uniquely mark the materials location (e.g., warehouse, container number, yard number, etc.) | DR010-01 Project Information
PK | Required | Location ID | Bin identifier for correct location of the item (e.g., warehouse location, shelf and bay or box) | DR020-01 Schedule Activities
| Optional | Facility Description | Description of the materials location | DR050-01 Equipment List
| Optional | Facility Site | Site where the materials location resides | DR070-01 Line List
| Optional | Facility Type | Type of location (e.g., warehouse, laydown, etc. ) | DR080-01 Pipe Components
DR090-01 Structures List
DR100-01 Cable Schedule
DR120-01 Document Register
DR140-01 EWP Estimate
DR150-01 Material Requisition Tracking
DR170-01 Steel Detailing Deliverables
DR180-01 Steel Fabrication CWP Tracking
DR190-01 Pipe Isometric Detailing
DR200-01 Pipe CWP Fabrication Delivery Requirements
DR230-01 Contractor Scope
DR260-01 Constraints
DR270-01 Materials Location
DR290-01 Rules of Credit
DR310-01 Sub-Systems Index

## DR270-02
AWP Site Materials
DR270-02 Material Receiving Report
Key | Tier | Field Name | Definition | Directory
PK | Required | Project ID | Unique project identifier | DR000-01 Requirements List
PK | Required | Material Receiving Report | Unique identifier of the delivery | DR010-01 Project Information
PK | Required | Shipment ID | Shipment identifier | DR020-01 Schedule Activities
PK | Required | Load List ID | Load list identifier | DR050-01 Equipment List
PK | Required | Container ID | Identifier of container, box, pallet, etc. | DR070-01 Line List
PK | Required | Material ID | Material identifier for the BOM item(s) (bulk) or unique tag ID if applicable (e.g., tag, spool number, commodity, etc.) | DR080-01 Pipe Components
| Required | PO | Purchase order number | DR090-01 Structures List
| Optional | Requisition Line Item | Line item on the requisition | DR100-01 Cable Schedule
| Required | Item Description | Material description | DR120-01 Document Register
| Optional | Date Received | Date material received - site takes custody | DR140-01 EWP Estimate
| Required | Expected Qty | Quantity of item identifier | DR150-01 Material Requisition Tracking
| Required | Expected Qty UOM | Unit of measurement for quantity of item (e.g., EA, LF, Dia. In, M, etc.) | DR170-01 Steel Detailing Deliverables
| Required | Qty Received | Total quantity received | DR180-01 Steel Fabrication CWP Tracking
| Optional | Qty Overage | Quantity overage of the received item(s) | DR190-01 Pipe Isometric Detailing
| Optional | Qty Shortage | Quantity shortage of the received item(s) | DR200-01 Pipe CWP Fabrication Delivery Requirements
| Optional | Qty Damage | Quantity damaged of the received item(s) | DR230-01 Contractor Scope
| Required | CWP | Unique construction work package identifier | DR260-01 Constraints
| Required | Tag | Unique tag number assigned to identify a project item | DR270-01 Materials Location
| Required | Discipline | Discipline responsible for the engineering design | DR290-01 Rules of Credit
| Optional | Material Category | Material category | DR310-01 Sub-Systems Index
| Optional | Material Type | Material type within the category
| Optional | Facility ID | Short identifier to uniquely mark the location of the materials (e.g., warehouse, container number, yard number, etc.)
| Optional | Location ID | Bin identifier for correct location of the item (e.g., warehouse location, shelf and bay or box)
| Optional | Material Size | Material sizing information
| Optional | Size UOM | Unit of measurement for material sizing (e.g., EA, LF, M, In, etc. )
| Optional | Weight | Weight of the item
| Optional | Weight UOM | Unit of measurement for weight of the item (e.g., TN, Lbs, Mt, Kg, etc.)

## DR270-03
AWP Site Materials
DR270-03 Materials Inventory
Key | Tier | Field Name | Definition | Directory
PK | Required | Project ID | Unique project identifier | DR000-01 Requirements List
PK | Required | Material ID | Material identifier for the BOM item(s) (bulk) or unique tag identifier, if applicable (e.g., tag, spool number, commodity, etc.) | DR010-01 Project Information
| Required | Item Description | Material description | DR020-01 Schedule Activities
| Optional | CWP | Unique construction work package identifier | DR050-01 Equipment List
| Optional | IWP | Unique installation work package identifier | DR070-01 Line List
| Required | Discipline | Discipline responsible for the engineering design | DR080-01 Pipe Components
| Required | Facility ID | Location identifier for the material item(s) | DR090-01 Structures List
| Required | Location ID | Bin identifier for correct location of the item (e.g., warehouse location, shelf and bay or box) | DR100-01 Cable Schedule
| Required | Material Category | Material category | DR120-01 Document Register
| Required | Material Description | Material description | DR140-01 EWP Estimate
| Required | Material Type | Material type within the category | DR150-01 Material Requisition Tracking
| Required | Qty Inventory | Current quantity in inventory at location | DR170-01 Steel Detailing Deliverables
| Required | Qty Issued | Quantity issued | DR180-01 Steel Fabrication CWP Tracking
| Required | Qty Purchased | Total quantity purchased for the project to date | DR190-01 Pipe Isometric Detailing
| Required | Qty Received | Total quantity received for the project to date | DR200-01 Pipe CWP Fabrication Delivery Requirements
| Required | QTY UOM | Unit of measurement for quantity of the item (e.g., Dia. In, M, etc.) | DR230-01 Contractor Scope
| Required | Tag | Unique tag number assigned to identify a project item | DR260-01 Constraints
| Optional | Material Size | Material sizing information | DR270-01 Materials Location
| Optional | Material Size UOM | Unit of measurement for material size (e.g., EA, LF, Dia. In, M, etc. ) | DR290-01 Rules of Credit
DR310-01 Sub-Systems Index

## DR270-04
AWP Site Materials
DR270-04 Materials Issue
Key | Tier | Field Name | Definition | Directory
PK | Required | Project ID | Unique project identifier | DR000-01 Requirements List
PK | Required | Materials Issue Request ID | Material requisition identifier for the materials issue request | DR010-01 Project Information
| Required | Material ID | Material identifier for the BOM item(s) | DR020-01 Schedule Activities
| Required | Material Description | Material description | DR050-01 Equipment List
| Required | Delivered To | Responsible stakeholder that the materials issue was provided to | DR070-01 Line List
| Required | Issued Date | Date of materials issue | DR080-01 Pipe Components
| Required | IWP | Unique installation work package identifier | DR090-01 Structures List
| Required | Qty Issued | Total quantity issued | DR100-01 Cable Schedule
| Required | Qty Requested | Total quantity requested for issue | DR120-01 Document Register
| Required | Qty Shortage | Total quantity shortage | DR140-01 EWP Estimate
| Required | QTY UOM | Unit of measurement for quantity (e.g., EA, LF, Dia. In, M, etc.) | DR150-01 Material Requisition Tracking
| Required | Requested By | Responsible stakeholder who requested the issuance of materials | DR170-01 Steel Detailing Deliverables
| Required | Requested Date | Date of materials issue request | DR180-01 Steel Fabrication CWP Tracking
| Required | Tag | Unique tag number that is assigned to identify a project item | DR190-01 Pipe Isometric Detailing
DR200-01 Pipe CWP Fabrication Delivery Requirements
DR230-01 Contractor Scope
DR260-01 Constraints
DR270-01 Materials Location
DR290-01 Rules of Credit
DR310-01 Sub-Systems Index

## DR290-01
AWP Site Progress
DR290-01 Rules of Credit
Key | Tier | Field Name | Definition | Directory
PK | Required | Project ID | Unique project identifier | DR000-01 Requirements List
PK | Required | IWP Type | Type of installation work package (e.g., install, hydrotest, etc.) | DR010-01 Project Information
PK | Required | Work Type | Type of work (e.g., spool, cable, foundation, etc.) | DR020-01 Schedule Activities
PK | Required | Work Sub Type | Subset of typical steps for a specific type grouping | DR050-01 Equipment List
PK | Required | Typical Step Number | Sequencing order for typical steps | DR070-01 Line List
| Required | Discipline | Discipline responsible for the engineering design | DR080-01 Pipe Components
| Required | Typical Step Description | Short description for the typical step (e.g., stage, erect, connect, support, punch) | DR090-01 Structures List
| Required | Typical Step Spread | Percentage spread factor that the typical step “earns” of Total QTY upon completion of the step | DR100-01 Cable Schedule
DR120-01 Document Register
DR140-01 EWP Estimate
DR150-01 Material Requisition Tracking
DR170-01 Steel Detailing Deliverables
DR180-01 Steel Fabrication CWP Tracking
DR190-01 Pipe Isometric Detailing
DR200-01 Pipe CWP Fabrication Delivery Requirements
DR230-01 Contractor Scope
DR260-01 Constraints
DR270-01 Materials Location
DR290-01 Rules of Credit
DR310-01 Sub-Systems Index

## DR290-02
AWP Site Progress
DR290-02 IWP Work Steps
Key | Tier | Field Name | Definition | Directory
PK | Required | Project ID | Unique project identifier | DR000-01 Requirements List
PK | Required | IWP | Unique installation work package identifier | DR010-01 Project Information
PK | Required | Tag | Unique tag number assigned to identify a project item | DR020-01 Schedule Activities
PK | Required | Work Step Number | Sequencing number of the work step in the IWP for the specified material component | DR050-01 Equipment List
| Required | Component or Assembly Name | Name for the component or assembly | DR070-01 Line List
| Required | Work Type | Type of work (e.g., spool, cable, foundation, etc.) | DR080-01 Pipe Components
| Required | Work Sub Type | Subset of typical steps for a specific type grouping | DR090-01 Structures List
| Required | Discipline | Discipline responsible for the engineering design | DR100-01 Cable Schedule
| Required | IWP Type | Type of installation work package (e.g., install, hydrotest, etc.) | DR120-01 Document Register
| Required | Percent Complete | Percentage complete of the specified work step | DR140-01 EWP Estimate
| Required | Total QTY | Total quantity of the specified material component in the specified IWP | DR150-01 Material Requisition Tracking
| Required | QTY UOM | Unit of measurement for the quantity reported (e.g., EA, LF, Dia. In, M, CY, etc.) | DR170-01 Steel Detailing Deliverables
| Required | Work Step Description | Short description of the work step | DR180-01 Steel Fabrication CWP Tracking
| Optional | Work Step Earnable QTY | Quantity “to earn” with 100% progress of the specified work step | DR190-01 Pipe Isometric Detailing
| Optional | Component or Assembly Description | Short description for the component or assembly | DR200-01 Pipe CWP Fabrication Delivery Requirements
| Optional | Total Budget HRS | Total budget hours of the specified material component in the specified IWP | DR230-01 Contractor Scope
DR260-01 Constraints
DR270-01 Materials Location
DR290-01 Rules of Credit
DR310-01 Sub-Systems Index

## DR290-03
AWP Site Progress
DR290-03 IWP Execution
Key | Tier | Field Name | Definition | Directory
PK | Required | Project ID | Unique project identifier | DR000-01 Requirements List
PK | Required | IWP | Unique installation work package identifier | DR010-01 Project Information
| Required | IWP - HRS Actual | Actual man-hours expended on IWP based upon actual installation work | DR020-01 Schedule Activities
| Required | IWP - HRS Earned | Total man-hours “earned” in the IWP based upon installed quantity and rules of progress | DR050-01 Equipment List
| Required | IWP - HRS To Go | Total man-hours to be able “to be earned” in the IWP based upon quantity of IWP scope | DR070-01 Line List
| Required | IWP Percentage Complete | Total percentage complete of work steps in the IWP | DR080-01 Pipe Components
| Required | IWP Start - Actual | Actual start date of the IWP in the short-range lookahead schedule | DR090-01 Structures List
| Required | IWP Start - Forecast | Forecast start date of the IWP in the short-range lookahead schedule | DR100-01 Cable Schedule
| Required | IWP Start - Plan | Planned start date of the IWP in the baseline lookahead schedule | DR120-01 Document Register
| Required | IWP Finish - Actual | Actual finish date of the IWP in the short-range lookahead schedule | DR140-01 EWP Estimate
| Required | IWP Finish - Forecast | Forecast finish date of the IWP in the short-range lookahead schedule | DR150-01 Material Requisition Tracking
| Required | IWP Finish - Plan | Planned finish date of the IWP in the baseline lookahead schedule | DR170-01 Steel Detailing Deliverables
DR180-01 Steel Fabrication CWP Tracking
DR190-01 Pipe Isometric Detailing
DR200-01 Pipe CWP Fabrication Delivery Requirements
DR230-01 Contractor Scope
DR260-01 Constraints
DR270-01 Materials Location
DR290-01 Rules of Credit
DR310-01 Sub-Systems Index

## DR290-04
AWP Site Progress
DR290-04 IWP Delays
Key | Tier | Field Name | Definition | Directory
PK | Required | Project ID | Unique project identifier | DR000-01 Requirements List
PK | Required | IWP | Unique installation work package identifier | DR010-01 Project Information
PK | Required | Tag | Unique tag number assigned to identify a project item | DR020-01 Schedule Activities
PK | Required | Work Step Number | Sequencing number of the work step in the IWP for the specified material component | DR050-01 Equipment List
PK | Required | Delay Code | Standard code used for trending reasons for the delay | DR070-01 Line List
PK | Required | Delay Date | Date that delay was captured | DR080-01 Pipe Components
| Required | IWP - HRS Delayed | Delayed man-hours wasted on IWP due to unforeseen field constraints stopping IWP close | DR090-01 Structures List
| Optional | Comments | Short description of the reason for delay and inability to close out the IWP | DR100-01 Cable Schedule
DR120-01 Document Register
DR140-01 EWP Estimate
DR150-01 Material Requisition Tracking
DR170-01 Steel Detailing Deliverables
DR180-01 Steel Fabrication CWP Tracking
DR190-01 Pipe Isometric Detailing
DR200-01 Pipe CWP Fabrication Delivery Requirements
DR230-01 Contractor Scope
DR260-01 Constraints
DR270-01 Materials Location
DR290-01 Rules of Credit
DR310-01 Sub-Systems Index

## DR310-01
AWP Completions
DR310-01 Sub-Systems Index
Key | Tier | Field Name | Definition | Directory
PK | Required | Project ID | Unique project identifier | DR000-01 Requirements List
PK | Required | Sub-System ID | Unique turnover sub-system identifier | DR010-01 Project Information
| Required | Sub-System Description | Description of the sub-system | DR020-01 Schedule Activities
| Required | Plan TCCC Date | Baseline plan date for transfer of care, custody, and control (TCCC) | DR050-01 Equipment List
| Required | Forecast TCCC Date | Current forecast date for TCCC | DR070-01 Line List
| Required | Actual TCCC Date | Actual date for TCCC | DR080-01 Pipe Components
| Required | Current Custody Status | Current status of the turnover system (e.g., construction, pre-com, CSU, client, etc.) | DR090-01 Structures List
| Optional | System Type | Type of system (e.g., process, fire detection, safety, telecom, etc.) | DR100-01 Cable Schedule
| Required | Related Tag | Related tag for the sub-system | DR120-01 Document Register
| Required | Related IWP | Related IWP for the sub-system | DR140-01 EWP Estimate
| Required | Related SWP | Related SWP for the sub-system | DR150-01 Material Requisition Tracking
| Required | Commissioning Zone ID | Unique commissioning zone identifier | DR170-01 Steel Detailing Deliverables
| Required | Commissioning Zone Description | Description of commissioning zone | DR180-01 Steel Fabrication CWP Tracking
| Required | System ID | Unique turnover system identifier | DR190-01 Pipe Isometric Detailing
| Required | System Description | Description of system | DR200-01 Pipe CWP Fabrication Delivery Requirements
DR230-01 Contractor Scope
DR260-01 Constraints
DR270-01 Materials Location
DR290-01 Rules of Credit
DR310-01 Sub-Systems Index

## DR310-02
AWP Completions
DR310-02 Test Packages
Key | Tier | Field Name | Definition | Directory
PK | Required | Project ID | Unique project identifier | DR000-01 Requirements List
PK | Required | Test Package ID | Unique test package identifier (e.g., hydrotest package) | DR010-01 Project Information
| Required | Sub-System ID | Unique turnover sub-system identifier | DR020-01 Schedule Activities
| Required | Plan Test Date | Baseline plan date for test | DR050-01 Equipment List
| Required | Actual Test Date | Actual date for test | DR070-01 Line List
| Required | Forecast Test Date | Current forecast date for test | DR080-01 Pipe Components
| Required | Test Status | Current status of the system test (e.g., construction, ready for test, complete, etc.) | DR090-01 Structures List
| Required | Test Type | Type of test to be performed (e.g., hydro, loop check, megger, etc.) | DR100-01 Cable Schedule
| Optional | Test Discipline | Responsible discipline for the test (e.g., piping, electrical, etc.) | DR120-01 Document Register
| Required | Related Tag | Related tag for the test package | DR140-01 EWP Estimate
| Required | Related IWP | Related installation work package for the test package | DR150-01 Material Requisition Tracking
| Required | Related SWP | Related system work package for the test package | DR170-01 Steel Detailing Deliverables
DR180-01 Steel Fabrication CWP Tracking
DR190-01 Pipe Isometric Detailing
DR200-01 Pipe CWP Fabrication Delivery Requirements
DR230-01 Contractor Scope
DR260-01 Constraints
DR270-01 Materials Location
DR290-01 Rules of Credit
DR310-01 Sub-Systems Index

## DR310-03
AWP Completions
DR310-03 Punch List Items
Key | Tier | Field Name | Definition | Directory
PK | Required | Project ID | Unique project identifier | DR000-01 Requirements List
PK | Required | Punch List | Identifies specific walkdown that the punch list was captured in (e.g., mechanical completion walkdown, commissioning walkdown, client turnover walkdown, etc.) | DR010-01 Project Information
PK | Required | Punch Item ID | Unique identifier used to track the punch list item | DR020-01 Schedule Activities
| Required | Punch Item Description | Description of the punch list item | DR050-01 Equipment List
| Required | Related Sub-System | Related sub-system package for the punch list item | DR070-01 Line List
| Required | Priority | Priorities as defined by project (e.g., A, B, C) | DR080-01 Pipe Components
| Required | Assigned Date | Date that the punch list item was assigned | DR090-01 Structures List
| Required | Assigned To | Individual that the punch list item was assigned to | DR100-01 Cable Schedule
| Required | Originator By | Individual or team that identified the punch list item | DR120-01 Document Register
| Required | Originator Date | Date that the punch list item was created | DR140-01 EWP Estimate
| Required | Resolution Date | Date that the punch list item was resolved | DR150-01 Material Requisition Tracking
| Required | Punch Item Status | Status of the punch list item (i.e., open or closed) | DR170-01 Steel Detailing Deliverables
| Optional | Originating IWP | IWP scope from which the punch item originated (e.g., IWP tag where valve tag was missing) | DR180-01 Steel Fabrication CWP Tracking
| Optional | Related Tag | Related equipment tag for the punch list item | DR190-01 Pipe Isometric Detailing
| Optional | Related Drawing | Related drawing for the punch list item | DR200-01 Pipe CWP Fabrication Delivery Requirements
| Optional | Exception Flag | Identifies whether punch list item will be received without completing | DR230-01 Contractor Scope
| Optional | Remarks | Any remarks or notes | DR260-01 Constraints
DR270-01 Materials Location
DR290-01 Rules of Credit
DR310-01 Sub-Systems Index

## DR310-04
AWP Completions
DR310-04 Check & Test Sheets
Key | Tier | Field Name | Definition | Directory
PK | Required | Project ID | Unique project identifier | DR000-01 Requirements List
PK | Required | Check & Test Sheet Number | Unique identifier of the check and test sheet | DR010-01 Project Information
| Required | Check & Test Sheet Description | Description of the check and test sheet | DR020-01 Schedule Activities
| Required | Check & Test Sheet Revision | Current revision of the check and test sheet | DR050-01 Equipment List
| Required | Check & Test Sheet Discipline | Discipline of the check and test sheet | DR070-01 Line List
| Required | Check & Test Sheet Type | Type of the check and test sheet | DR080-01 Pipe Components
| Required | Originator | Name of the originator | DR090-01 Structures List
| Required | Document Type | Type of document | DR100-01 Cable Schedule
| Required | Related Sub-System | Related sub-system package for the check and test sheet | DR120-01 Document Register
| Required | Priority | Priorities as defined by project (e.g., A, B, C) | DR140-01 EWP Estimate
| Required | Check & Test Sheet Status | Status of the check and test sheet (i.e., open or closed) | DR150-01 Material Requisition Tracking
| Required | Related IWP | Related installation work package for the check and test sheet | DR170-01 Steel Detailing Deliverables
| Required | Related SWP | Related system work package for the check and test sheet | DR180-01 Steel Fabrication CWP Tracking
| Required | Related Tag | Related equipment tag for the check and test sheet | DR190-01 Pipe Isometric Detailing
| Optional | Related Drawing | Related drawing for the check and test sheet | DR200-01 Pipe CWP Fabrication Delivery Requirements
| Optional | Remarks | Any remarks or notes | DR230-01 Contractor Scope
DR260-01 Constraints
DR270-01 Materials Location
DR290-01 Rules of Credit
DR310-01 Sub-Systems Index